## Sheet1
| Task | Status | Comments | Periode
Deliverable I | The Adopt-A-Well console is finalized on mWater, and all the feedback collected are integrated. | done
Deliverable II | The Commune Action Plan console (allowing us to query the Commune Action Plan data for Cavaillon, Ferrier, Leogane, Pignon, and Terre-Neuve) is completed on mWater, and feedback are collected and integrated. | done
Deliverable III | The training materials associated with the Adopt-A-Well console and the Commune Acton Plan Console are completed and two training sessions are delivered to the HANWASH volunteers (one for each console). | On-Going | 1. Both Training materials are ready. 2. Training sessions for the AAW console has been conducted successfully. 3. Training sessions for the CAP has not been conducted yet. | - periode: 01/07 - 10/07 -> wait for CAP training materials approval. -> Initiate the invites with the stakeholders. -> Execute the training session with each this said week or before the 10/07.
Deliverable IV | One console is created on mWater to view/query data associated with the operaton of the water systems rehabilitated by HANWASH, particularly the Pignon town water utlity. • Feedback are collected from the relevant HANWASH stakeholders and they are integrated in the console to finalize it. | On-Going | 1. We have started with the MAP of the water system (improvement can be possible). 2. We come up with a work around to get workable data for the other components of the console. 3. Given the dinepa indicators, we are expecting at least 2 more components | - periode: 01/07 - 12/07 -> expect near completion of the console this friday 05. -> Expect to be ready before the 12/07
Deliverable V | One mWater page is created to allow the local authorities (ASEC, CASEC, Mayor) and OREPA representative to view/query the monthly reports submitted by the CPEs. • Feedback are collected from the relevant HANWASH stakeholders (Hai3 Liaison, ASEC, CASEC, Mayor, EPAC, etc.) and they are integrated in the page to finalize it. | Not Started |  | - periode 08/07 - 19/07 -> start the planning with the team (probably on the 11/07) -> work on the console, expect a full version on the 19/07
Deliverable VI | A user guide is created for the mWater page related to the CPE monthly reports, and a training session is delivered to Haiti Liaison, local authorities (ASEC, CASEC, Mayor, etc.) and OREPA representative. | Not Started |  | - 20/07 - 22/07 Completion of the training materials
Deliverable VII | One (1) console is created on mWater to visualize/query the data related to the progress towards the indicators in the Mattson Program’s Indicator framework. • Feedback are collected from the relevant HANWASH stakeholders (Haiti Liaison, M&E Subcommittee Leaders, HANWASH Ambassadors, D 7020 Subcommitee Leaders.) and they are integrated in the console to finalize it • A user guide associated with this specific console is created and a training session is delivered to HANWASH volunteers. | Not Started |  | - periode: 29/07 - 15/08 -> plan the console -> work on the console, expect a full version 08/08 -> build the user guides (09/08 - 11/08) -> 12/08 - 15/08, any training session or ongoing task are expected to be fully completed.
| • Contribute to the overall development of the mWater database as a user-friendly portal for HANWASH volunteers and staff to easily access project data, regardless of whether it is the construction or the opera3ons period. • Provide support as needed in planning and conduc3ng the baseline study for the Ma_son Program. | Constant |  | will end the 15/08