## Sheet1
ID | Indicator_group | Category | Category_code | Category_code_description | Indicator | Definitions | Units | Baseline_value | End_of_program_target | Year1_target | Year1_actual | Year2_target | Year2_actual | Year3_target | Year3_actual | Year4_target | Year4_actual | Year5_target | Year5_actual
1 | Mattson LM | Ultimate outcome | 1 | Increased access to safe, sustainable and affordable water, sanitation and hygiene (WASH) services in Haiti​. | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Mattson LM | Intermediate outcome | 1000 | Strengthened demand for and management of WASH services in communes. | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1100a | Mattson LM | Immediate outcome | 1100 | Increased civil society engagement in decision making and implementation of WASH services. | % of commune WASH events with Rotarian participation | Percentage of commune-level WASH events that have active Rotarian participation, measured as a proportion of total reported events. | % | 20 | 100 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 99 | 99
1100b | Mattson LM | Immediate outcome | 1100 | Increased civil society engagement in decision making and implementation of WASH services. | % of commune WASH events led by trained HANWASH Ambassadors and Coordinators to communicate WASH messages and advocate for HANWASH goal | Percentage of commune-level WASH events led by trained HANWASH Ambassadors and Coordinators to communicate WASH messages and advocate for HANWASH goals, measured as a proportion of total reported events. | % | 20 | 100 | 26 | 23 | 26 | 26 | 38 | 20 | 41 | 34 | 49 | 77
1110a | Mattson LM | Outputs | 1110 | Support civil society engagement in the WASH sector.​ | # of volunteer hours per month spent by Rotarians in WASH events | Average number of volunteer hours per month spent by Rotarians in WASH events, calculated per Rotary club. | volunteer hours / club / month | 1 | 100 | 1 | 1 | 1 | 1 | 16 | 3 | 39 | 19 | 47 | 80
1110b | Mattson LM | Outputs | 1110 | Support civil society engagement in the WASH sector.​ | Number of people reached by the HANWASH Ambassadors, Coordinators and Rotarians in general in the Commune WASH events and advocacy efforts led by them | Total number of individuals reached through WASH events and advocacy efforts led by HANWASH Ambassadors, Coordinators, and Rotarians in the commune. | people | 1 | 100 | 1 | 1 | 1 | 1 | 2 | 2 | 8 | 3 | 92 | 97
1120a | Mattson LM | Outputs | 1120 | Train HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean.​ | # of ambassadors who have completed training | Total number of HANWASH Ambassadors who have successfully completed the required training program. | people | 1 | 100 | 1 | 1 | 2 | 1 | 2 | 2 | 8 | 3 | 91 | 97
1120b | Mattson LM | Outputs | 1120 | Train HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean.​ | # of coordinators who have completed training | Total number of HANWASH Coordinators who have successfully completed the required training program. | people | 1 | 100 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 99 | 100
1120c | Mattson LM | Outputs | 1120 | Train HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean.​ | # of training materials created in alignment with HANWASH three pillars and core values | Number of training materials developed that align with HANWASH's three pillars and core values. | Training materials | 1 | 20 | 1 | 1 | 1 | 1 | 3 | 1 | 6 | 3 | 13 | 18
1120d | Mattson LM | Outputs | 1120 | Train HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean.​ | # of hours of training received by the HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean | Cumulative number of training hours received by HANWASH Ambassadors, Coordinators, and their committees throughout the Caribbean region. | Hours of training | 1 | 40 | 2 | 1 | 7 | 3 | 8 | 4 | 8 | 4 | 19 | 32
1200a | Mattson LM | Immediate outcome | 1200 | Improved commune WASH planning and coordination by local authorities.​ | % of approved interventions implemented in alignment with Commune Action Plans | Percentage of implemented interventions that align with approved Commune Action Plans, indicating adherence to local priorities and needs. | % | 20 | 100 | 20 | 20 | 27 | 26 | 31 | 22 | 41 | 32 | 61 | 80
1210a | Mattson LM | Outputs | 1210 | Create or improve commune action plans that focus on water, sanitation and hygiene, and water resource management.​ | # of communes with action plans that explicitly include each W,S,H,WRM aspect (water, sanitation, hygiene, water resources management) | Number of communes with comprehensive action plans that explicitly address all four WASH aspects: Water, Sanitation, Hygiene, and Water Resources Management. | communes | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 11 | 11
1220a | Mattson LM | Outputs | 1220 | Facilitate coordination meetings between commune WASH stakeholders. | # of WASH planning and coordination events with DINEPA and municipal officials | Number of WASH planning and coordination events conducted with DINEPA and municipal officials per month, fostering collaboration and alignment. | events/month | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 9 | 9
1300a | Mattson LM | Immediate outcome | 1300 | Improved accountability of service providers to users of WASH services.​ | % of service providers under HANWASH initiative monitored according to national guidelines | Percentage of service providers under the HANWASH initiative that are monitored according to national guidelines, ensuring compliance and quality. | % | 20 | 100 | 26 | 25 | 26 | 23 | 39 | 25 | 41 | 37 | 48 | 70
1300b | Mattson LM | Immediate outcome | 1300 | Improved accountability of service providers to users of WASH services.​ | % of intervention service providers with accountability structures in place | Percentage of intervention service providers that have established accountability structures, promoting transparency and community engagement. | % | 20 | 100 | 26 | 23 | 29 | 22 | 29 | 21 | 29 | 21 | 67 | 93
1300c | Mattson LM | Immediate outcome | 1300 | Improved accountability of service providers to users of WASH services.​ | % of users being satisfied with the quality, affordability and reliability of the WASH services provided | Percentage of users expressing satisfaction with the quality, affordability, and reliability of WASH services provided, based on household surveys. | % | 20 | 100 | 20 | 20 | 21 | 21 | 23 | 22 | 40 | 36 | 76 | 81
1310a | Mattson LM | Outputs | 1310 | Monitor WASH service performance and satisfaction. | # of intervention water systems regularly reporting data | Number of intervention water systems that consistently report data on a regular basis, demonstrating operational transparency. | water systems | 1 | 10 | 1 | 1 | 1 | 1 | 2 | 2 | 5 | 5 | 5 | 5
1310b | Mattson LM | Outputs | 1310 | Monitor WASH service performance and satisfaction. | % of customer complaints resolved during the month | Percentage of customer complaints resolved during the month, calculated as (number of resolved complaints / total number of complaints) * 100. | % | 20 | 100 | 23 | 20 | 28 | 22 | 30 | 21 | 31 | 21 | 68 | 96
1310c | Mattson LM | Outputs | 1310 | Monitor WASH service performance and satisfaction. | Average response time to resolve customer complaints | Average number of days taken to resolve customer complaints, indicating responsiveness and service quality. | Days | 7 | 21 | 7 | 7 | 9 | 7 | 9 | 7 | 11 | 9 | 13 | 19
2000 | Mattson LM | Intermediate outcome | 2000 | Enhanced household access to and use of sustainable, affordable, and safe water, sanitation and hygiene services.​ | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2100a | Mattson LM | Immediate outcome | 2100 | Increased household access to sustainable, affordable, and safe drinking water services.​ | % of intervention water points which are functioning and potable | Percentage of intervention water points that are both functioning and providing potable water, ensuring access to safe drinking water. | % | 20 | 100 | 20 | 20 | 20 | 20 | 22 | 21 | 23 | 22 | 95 | 97
2100b | Mattson LM | Immediate outcome | 2100 | Increased household access to sustainable, affordable, and safe drinking water services.​ | % of population in intervention communes with at least basic drinking water service | Percentage of population in intervention communes with access to at least basic drinking water service, defined as an improved water source within 30 minutes round trip. | % | 20 | 100 | 22 | 22 | 23 | 23 | 31 | 30 | 32 | 20 | 72 | 85
2100c | Mattson LM | Immediate outcome | 2100 | Increased household access to sustainable, affordable, and safe drinking water services.​ | % of population in intervention communes with safely managed drinking water service | Percentage of population in intervention communes with access to safely managed drinking water service, defined as an improved water source on premises, available when needed, and free from contamination. | % | 20 | 100 | 20 | 20 | 20 | 20 | 33 | 30 | 41 | 20 | 66 | 90
2100d | Mattson LM | Immediate outcome | 2100 | Increased household access to sustainable, affordable, and safe drinking water services.​ | % of intervention water points which are functional, potable, and have a balanced budget or a budget with surplus after 2 years | Percentage of intervention water points that are functioning, potable, and financially sustainable (balanced or surplus budget) after 2 years of operation. | % | 20 | 100 | 26 | 24 | 26 | 22 | 33 | 25 | 38 | 24 | 57 | 85
2110a | Mattson LM | Outputs | 2110 | Develop community managed water points. | # of people in intervention communes with access to basic drinking water service through community managed water points | Number of people in intervention communes gaining access to basic drinking water service through community-managed water points. | people | 1 | 100 | 2 | 1 | 2 | 2 | 12 | 5 | 29 | 29 | 59 | 67
2110b | Mattson LM | Outputs | 2110 | Develop community managed water points. | # of community managed water points created | Number of new community-managed water points created, with signed CPE statutes with DINEPA. | water points | 1 | 200 | 14 | 6 | 23 | 17 | 38 | 13 | 62 | 3 | 67 | 165
2110c | Mattson LM | Outputs | 2110 | Develop community managed water points. | % of the community managed water points created which submit report to local authorities on a monthly basis | Percentage of newly created community-managed water points that submit monthly reports to local authorities, promoting accountability. | water points | 1 | 200 | 3 | 1 | 4 | 1 | 15 | 10 | 70 | 50 | 112 | 142
2120a | Mattson LM | Outputs | 2120 | Rehabilitate and expand professionally operated piped water systems. | # of people added to safely managed drinking water service | Number of people newly provided with safely managed drinking water service, meeting WHO/UNICEF Joint Monitoring Programme (JMP) criteria. | people | 1 | 100 | 1 | 1 | 2 | 2 | 5 | 1 | 37 | 32 | 59 | 68
2120c | Mattson LM | Outputs | 2120 | Rehabilitate and expand professionally operated piped water systems. | # of professionally managed piped water systems rehabilitated in the intervention communes | Number of professionally managed piped water systems rehabilitated in the intervention communes, improving existing infrastructure. | water systems | 1 | 10 | 1 | 1 | 1 | 1 | 2 | 1 | 4 | 1 | 6 | 10
2120b | Mattson LM | Outputs | 2120 | Rehabilitate and expand professionally operated piped water systems. | # of professionally managed piped water systems created in the intervention communes | Number of new professionally managed piped water systems created in the intervention communes, expanding water service coverage. | water systems | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 9 | 10
2200a | Mattson LM | Immediate outcome | 2200 | Increased household access to sustainable, affordable, and safe sanitation services.​ | % of intervention communities which are verified ODF | Percentage of intervention communities verified as Open Defecation Free (ODF), meeting all criteria set by the commune WASH committee. | % | 20 | 100 | 20 | 20 | 22 | 22 | 23 | 22 | 23 | 23 | 92 | 93
2200b | Mattson LM | Immediate outcome | 2200 | Increased household access to sustainable, affordable, and safe sanitation services.​ | % of population in intervention communes with at least basic sanitation service | Percentage of population in intervention communes with access to at least basic sanitation service, defined as improved and unshared facilities. | % | 20 | 100 | 20 | 20 | 20 | 20 | 20 | 20 | 24 | 20 | 96 | 100
2200c | Mattson LM | Immediate outcome | 2200 | Increased household access to sustainable, affordable, and safe sanitation services.​ | % of population in intervention communes with safely managed sanitation service | Percentage of population in intervention communes with access to safely managed sanitation service, meeting WHO/UNICEF JMP criteria. | % | 20 | 100 | 20 | 20 | 20 | 20 | 20 | 20 | 56 | 51 | 64 | 69
2210a | Mattson LM | Outputs | 2210 | Mobilize communities to achieve Open Defecation Free status | # of people added to basic sanitation service in the intervention communes | Number of people newly provided with access to basic sanitation service in the intervention communes. | people | 1 | 100 | 1 | 1 | 3 | 2 | 3 | 2 | 14 | 5 | 83 | 94
2210b | Mattson LM | Outputs | 2210 | Mobilize communities to achieve Open Defecation Free status | # of "intervention" communities verified ODF | Number of intervention communities that have been verified as Open Defecation Free (ODF) by the commune WASH committee. | communities | 1 | 200 | 2 | 1 | 4 | 1 | 4 | 4 | 13 | 11 | 181 | 187
2220a | Mattson LM | Outputs | 2220 | Certify the sustained usage of sanitation services. | # of "intervention" communities certified ODF | Number of intervention communities that have been certified as Open Defecation Free (ODF), maintaining verified ODF status for at least one year. | communities | 1 | 200 | 1 | 1 | 2 | 1 | 44 | 11 | 54 | 13 | 103 | 178
2230a | HANWASH-Master LM | Outputs | 2230 | Construct public latrines. | # of public latrines constructed | Number of public latrines constructed, improving sanitation access in communal areas. | toilet blocks | 1 | 150 | 1 | 1 | 1 | 1 | 1 | 1 | 53 | 25 | 98 | 126
2300a | Mattson LM | Immediate outcome | 2300 | Increased household access to hygiene services. | % of population in intervention communes with at least basic hygiene service | Percentage of population in intervention communes with access to at least basic hygiene service, defined as presence of a handwashing facility with soap and water on premises. | % | 20 | 100 | 24 | 21 | 31 | 26 | 37 | 23 | 40 | 23 | 48 | 87
2300b | Mattson LM | Immediate outcome | 2300 | Increased household access to hygiene services. | % of population in intervention communes with basic hygiene service | Percentage of population in intervention communes with access to basic hygiene service, as defined by WHO/UNICEF JMP criteria. | % | 20 | 100 | 21 | 21 | 23 | 20 | 39 | 26 | 40 | 34 | 57 | 79
2310a | Mattson LM | Outputs | 2310 | Train skilled community animators to deliver hygiene trainings and community mobilization.​ | # of community animators trained | Number of community animators trained to provide hygiene education and community mobilization. | animators | 1 | 100 | 1 | 1 | 16 | 12 | 17 | 17 | 18 | 16 | 52 | 58
2310b | Mattson LM | Outputs | 2310 | Train skilled community animators to deliver hygiene trainings and community mobilization.​ | # of hours of hygiene trainings and community mobilization provided by the community animators trained | Cumulative number of hours of hygiene training and community mobilization provided by trained community animators. | Hours | 1 | 100 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 1 | 95 | 97
2320a | Mattson LM | Outputs | 2320 | Certify the sustained usage of hygiene services. | # of people added to basic hygiene service | Number of people newly provided with access to basic hygiene service in intervention areas. | people | 1 | 100 | 2 | 2 | 3 | 2 | 3 | 3 | 42 | 10 | 54 | 87
2400a | HANWASH-Master LM | Immediate outcome | 2400 | Increased access to sustainable, safe drinking water, sanitation, and hygiene materials in healthcare facilities, schools, and public places. | % of schools with basic drinking water, sanitation, and hygiene services | Percentage of schools in intervention areas with basic drinking water, sanitation, and hygiene services, meeting WHO/UNICEF JMP criteria for schools. | % | 20 | 100 | 20 | 20 | 20 | 20 | 21 | 21 | 24 | 23 | 95 | 96
2400b | HANWASH-Master LM | Immediate outcome | 2400 | Increased access to sustainable, safe drinking water, sanitation, and hygiene materials in healthcare facilities, schools, and public places. | % of healthcare facilities with basic drinking water, sanitation, and hygiene services | Percentage of healthcare facilities in intervention areas with basic drinking water, sanitation, and hygiene services, meeting WHO/UNICEF JMP criteria for healthcare facilities. | % | 20 | 100 | 20 | 20 | 20 | 20 | 22 | 22 | 51 | 36 | 67 | 82
2410a | HANWASH-Master LM | Outputs | 2410 | Construct or rehabilitate water supply for healthcare facilities and schools. | # of schools added with basic drinking water services | Number of schools newly provided with basic drinking water services in intervention areas. | schools | 1 | 200 | 1 | 1 | 2 | 1 | 14 | 6 | 77 | 17 | 110 | 179
2410b | HANWASH-Master LM | Outputs | 2410 | Construct or rehabilitate water supply for healthcare facilities and schools. | # of healthcare facilities added with basic drinking water services | Number of healthcare facilities newly provided with basic drinking water services in intervention areas. | healthcare facilities | 1 | 200 | 1 | 1 | 1 | 1 | 7 | 5 | 9 | 2 | 186 | 195
2420a | HANWASH-Master LM | Outputs | 2420 | Construct communal, healthcare facility, and school latrines. | # of schools added with basic sanitation services | Number of schools newly provided with basic sanitation services in intervention areas. | schools | 1 | 200 | 6 | 5 | 6 | 5 | 12 | 7 | 83 | 18 | 97 | 169
2420b | HANWASH-Master LM | Outputs | 2420 | Construct communal, healthcare facility, and school latrines. | # of healthcare facilities added with basic sanitation services | Number of healthcare facilities newly provided with basic sanitation services in intervention areas. | healthcare facilities | 1 | 200 | 1 | 1 | 3 | 2 | 4 | 4 | 59 | 13 | 137 | 184
2430a | HANWASH-Master LM | Outputs | 2430 | Work with (local authorities, civil society) to ensure access to soap or alcohol-based handrub at schools and healthcare facilities. | # of schools added with basic hygiene | Number of schools newly provided with basic hygiene services in intervention areas. | schools | 1 | 200 | 5 | 5 | 21 | 6 | 22 | 17 | 34 | 15 | 122 | 161
2430b | HANWASH-Master LM | Outputs | 2430 | Work with (local authorities, civil society) to ensure access to soap or alcohol-based handrub at schools and healthcare facilities. | # of healthcare facilities added with basic hygiene | Number of healthcare facilities newly provided with basic hygiene services in intervention areas. | healthcare facilities | 1 | 200 | 1 | 1 | 1 | 1 | 6 | 3 | 90 | 80 | 106 | 119
3000 | Mattson LM | Intermediate outcome | 3000 | Expanded reach and resources leveraged through collective action with other national and international actors.​ | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3100a | Mattson LM | Immediate outcome | 3100 | Increased government and non-government funding in alignment with HANWASH Core Values. | Cumulative amount of money committed in alignment with HANWASH Core Values | Cumulative amount of money (in USD) committed to projects aligned with HANWASH Core Values, including local leadership, collaboration, systematic approach, impact, and commitment. | USD | 500 | 20000 | 1039 | 568 | 1058 | 1037 | 2483 | 1014 | 7685 | 6776 | 9735 | 12605
3100b | Mattson LM | Immediate outcome | 3100 | Increased government and non-government funding in alignment with HANWASH Core Values. | % of committed money which has been spent (cumulative) | Percentage of committed funds that have been spent, calculated as (Cumulative_amount_spent / Cumulative_amount_committed) * 100. | % | 20 | 100 | 22 | 20 | 32 | 21 | 37 | 25 | 39 | 34 | 50 | 80
3110a | Mattson LM | Outputs | 3110 | Mobilize and coordinate funding from government and non-government sources in HANWASH program areas in alignment with HANWASH Core Values. | Amount of money spent by external actors within HANWASH project areas | Amount of money (in USD) spent by external actors within HANWASH project areas, aligned with HANWASH Core Values. | USD | 500 | 20000 | 1479 | 1394 | 3059 | 677 | 5401 | 1915 | 5594 | 1046 | 6467 | 16968
3120a | HANWASH-Master LM | Outputs | 3120 | Mobilize and influence funding from government and non-government sources beyond HANWASH program areas in alignment with HANWASH Core Values. | Amount of money spent by external actors beyond project areas in alignment with HANWASH Core Values | Amount of money (in USD) spent by external actors beyond HANWASH project areas but still aligned with HANWASH Core Values, extending impact. | USD | 500 | 20000 | 1449 | 1391 | 2418 | 2173 | 4232 | 4175 | 6192 | 620 | 7709 | 13641
3200a | Mattson LM | Immediate outcome | 3200 | Increased capacity of DINEPA to regulate the sector and OREPA to oversee and support implementation. | % of implementing partners in HANWASH program areas who have signed the DINEPA Accord Cadre | Percentage of implementing partners in HANWASH program areas who have signed the DINEPA Accord Cadre, ensuring alignment with national standards. | % | 20 | 100 | 20 | 20 | 21 | 20 | 32 | 32 | 41 | 21 | 66 | 87
3210a | Mattson LM | Outputs | 3210 | Conduct leadership training of DINEPA and OREPA personnel. | # of DINEPA personnel trained as leaders | Number of DINEPA personnel who have completed leadership training, building capacity within the national water authority. | people | 1 | 100 | 2 | 1 | 2 | 1 | 5 | 4 | 47 | 21 | 48 | 77
3220a | Mattson LM | Outputs | 3220 | Provide technical assistance and training to DINEPA and the OREPAs. | # of technical trainings provided for DINEPA priority areas | Number of technical trainings provided for DINEPA priority areas, focusing on key topics such as unified national tariff methodology and ODF certification. | trainings | 1 | 100 | 7 | 2 | 9 | 7 | 13 | 10 | 21 | 7 | 54 | 78