## Master LM
Organization: HANWASH |  |  |  | Legend
Document: Master logic model |  |  |  | Active objectives - Included in current action plan
Objective: Define the objectives of the program. |  |  |  | Inactive objectives - Not included in current action plan
Scope: HANWASH programs
Reference link: Click here
Version number: 2.4
Version date: Sept. 11, 2023
Notes: The lower level objectives should cause the higher level objectives.
Objectives
Type | Description
Ultimate outcome | 1
Increased access to safe, sustainable and affordable water, sanitation and hygiene (WASH) services in Haiti​.
Intermediate outcomes | 1000 |  |  | 2000 |  |  |  | 3000
| Strengthened demand for and management of WASH services in communes. |  |  | Enhanced household access to and use of sustainable, affordable, and safe water, sanitation and hygiene services.​ |  |  |  | Expanded reach and resources leveraged through collective action with other national and international actors.​
Immediate outcomes | 1100 | 1200 | 1300 | 2100 | 2200 | 2300 | 2400 | 3100 | 3200
| Increased civil society engagement in decision making and implementation of WASH services. | Improved commune WASH planning and coordination by local authorities.​ | Improved accountability of service providers to users of WASH services.​ | Increased household access to sustainable, affordable, and safe drinking water services.​ | Increased household access to sustainable, affordable, and safe sanitation services.​ | Increased household access to hygiene services. | Increased access to sustainable, safe drinking water, sanitation, and hygiene materials in healthcare facilities, schools, and public places. | Increased government and non-government funding in alignment with HANWASH Core Values. | Increased capacity of DINEPA to regulate the sector and OREPA to oversee and support implementation.
Outputs | 1110 | 1210 | ​1310 | 2110 | 2210 | 2310 | 2410 | 3110 | 3210
| Support civil society engagement in the WASH sector.​ | Create or improve commune action plans that focus on water, sanitation and hygiene, and water resource management.​ | Monitor WASH service performance and satisfaction. | Develop community managed water points. | Mobilize communities to achieve Open Defecation Free status | Train skilled community animators to deliver hygiene trainings and community mobilization.​ | Construct or rehabilitate water supply for healthcare facilities and schools. | Mobilize and coordinate funding from government and non-government sources in HANWASH program areas in alignment with HANWASH Core Values. | Conduct leadership training of DINEPA and OREPA personnel.
| 1120 | 1220 | 1320 | 2120 | 2220 | 2320 | 2420 | 3120 | 3220
| Train HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean.​ | Facilitate coordination meetings between commune WASH stakeholders. | Review service provider performance with stakeholders. | Rehabilitate and expand professionally operated piped water systems. | Certify the sustained usage of sanitation services. | Certify the sustained usage of hygiene services. | Construct communal, healthcare facility, and school latrines. | Mobilize and influence funding from government and non-government sources beyond HANWASH program areas in alignment with HANWASH Core Values. | Provide technical assistance and training to DINEPA and the OREPAs.
[5 empty] | 2230 |  | 2430
[5 empty] | Construct public latrines. |  | Work with (local authorities, civil society) to ensure access to soap or alcohol-based handrub at schools and healthcare facilities.

## Mattson LM
Organization: HANWASH
Document: Mattson logic model
Objective: Define the objectives of the program.
Scope: Mattson Program
Reference link: Click here
Version number: 2.5
Version date: January 30, 2024
Notes: The lower level objectives should cause the higher level objectives. Objectives 2230, 2400,2410,2420,2430 are not in the scope of this program.
| Type | Description
| Ultimate outcome | 1
Increased access to safe, sustainable and affordable water, sanitation and hygiene (WASH) services in Haiti​.
| Intermediate outcomes | 1000 |  |  | 2000 |  |  | 3000
|  | Strengthened demand for and management of WASH services in communes. |  |  | Enhanced household access to and use of sustainable, affordable, and safe water, sanitation and hygiene services.​ |  |  | Expanded reach and resources leveraged through collective action with other national and international actors.​
| Immediate outcomes | 1100 | 1200 | 1300 | 2100 | 2200 | 2300 | 3100 | 3200
|  | Increased civil society engagement in decision making and implementation of WASH services. | Improved commune WASH planning and coordination by local authorities.​ | Improved accountability of service providers to users of WASH services.​ | Increased household access to sustainable, affordable, and safe drinking water services.​ | Increased household access to sustainable, affordable, and safe sanitation services.​ | Increased household access to hygiene services. | Increased government and non-government funding in alignment with HANWASH Core Values. | Increased capacity of DINEPA to regulate the sector and OREPA to oversee and support implementation.
| Outputs | 1110 | 1210 | ​1310 | 2110 | 2210 | 2310 | 3110 | 3210
|  | Support civil society engagement in the WASH sector.​ | Create or improve commune action plans that focus on water, sanitation and hygiene, and water resource management.​ | Monitor WASH service performance and satisfaction. | Develop community managed water points. | Mobilize communities to achieve Open Defecation Free status | Train skilled community animators to deliver hygiene trainings and community mobilization.​ | Mobilize and coordinate funding from government and non-government sources in HANWASH program areas in alignment with HANWASH Core Values. | Conduct leadership training of DINEPA and OREPA personnel.
|  | 1120 | 1220 | 1320 | 2120 | 2220 | 2320 | 3120 | 3220
|  | Train HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean.​ | Facilitate coordination meetings between commune WASH stakeholders. | Review service provider performance with stakeholders. | Rehabilitate and expand professionally operated piped water systems. | Certify the sustained usage of sanitation services. | Certify the sustained usage of hygiene services. | Mobilize and influence funding from government and non-government sources beyond HANWASH program areas in alignment with HANWASH Core Values. | Provide technical assistance and training to DINEPA and the OREPAs.

## Indicator framework
Organization: HANWASH |  |  |  | Legend
Document: Indicator framework |  |  |  | TBD' To be determined | '-' Not applicable
Objective: Define indicators to measure progress towards each objective.
Scope: HANWASH programs |  |  |  | Objective types | Description
Reference link: This document |  |  |  | Ultimate outcome | The highest level objective of HANWASH. These are not directly measureable by SMART indicators, but measured indirectly via indicators of their component Intermediate Outcomes.
Version number: 2.41 |  |  |  | Intermediate outcome | The component objectives of the HANWASH ultimate outcome. These are not directly measureable by SMART indicators, but measured indirectly via indicators of their component Intermediate Outcomes.
Version date: March 21, 2024 |  |  |  | Immediate outcome | The higher level objective that HANWASH seeks to achieve, which are able to be measured directly by SMART indicators. Indicators measuring these outcomes are typically expressed as a percent, which are harder to measure, but builds the context into the measure.
Notes: SMART indicators are indicators which are specific, measureable, achievable, relevant, and time-bound. |  |  |  | Output | The lower level objective that HANWASH seeks to achieve. Indicators measuring these outcomes are typically expressed as a number, which is easier to measure, but also easier to take out of context.
Objective |  |  | Indicator | [6 empty] | Reporting system |  |  |  | Commune validation |  | Reporting system validation |  |  |  | Notes
Type | Code | Description | Code_index | Description | Definitions | Units | Status | Program | (Dis)Aggregation | Source | Enumerator | Frequency | Visualization | Data source | Data collection | Source | Validator | Frequency | Visualization
Ultimate outcome | 1 | Increased access to safe, sustainable and affordable water, sanitation and hygiene (WASH) services in Haiti​. | - | - | - | - | - | Mattson | - | - | - | - | - | - | - | - | - | - | - | This objective is split into its component objectives and measured via their indicators
Intermediate outcome | 1000 | Strengthened demand for and management of WASH services in communes. | - | - | - | - | - | Mattson | - | - | - | - | - | - | - | - | - | - | - | This objective is split into its component objectives and measured via their indicators
Immediate outcome | 1100 | Increased civil society engagement in decision making and implementation of WASH services. | 1100a | % of commune WASH events with Rotarian participation | - | % of commune level events reported | In service - Needs training | Mattson | Event type, participant group, date, commune | Implementation event tracking form | Rotary ambassadors | After every implementation event | Implementation monitoring console |  |  | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of an exhaustive desk review of both the PMO and Rotarians forms.
Immediate outcome | 1100 | Increased civil society engagement in decision making and implementation of WASH services. | 1100b | % of commune WASH events led by trained HANWASH Ambassadors and Coordinators to communicate WASH messages and advocate for HANWASH goal | "…led by Rotarians…" means the WASH activities whose initiative have been taken by Rotarians. | % of commune level WASH events reported | Not started | Mattson | Event type, participant group, date, commune | Implementation event tracking form | Rotary ambassadors | After every implementation event | Implementation monitoring console | Review of existing data | HANWASH M&E officer | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console
Outputs | 1110 | Support civil society engagement in the WASH sector.​ | 1110a | # of volunteer hours per month spent by Rotarians in WASH events |  | volunteer hours / club / month | In service - Needs training | Mattson | Event type, participant group, date, commune | Implementation event tracking form | Rotary ambassadors | After every implementation event | Implementation monitoring console |  |  | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of an exhaustive desk review of both the PMO and Rotarians forms.
Outputs | 1110 | Support civil society engagement in the WASH sector.​ | 1110b | Number of people reached by the HANWASH Ambassadors, Coordinators and Rotarians in general in the Commune WASH events and advocacy efforts led by them | "Number of people reached…": Number of people participating in the WASH events led by Rotarians. | people | In service - Needs training | Mattson | Event type, participant group, date, commune | Implementation event tracking form | Rotary ambassadors | After every implementation event | Implementation monitoring console | Review of existing data | HANWASH M&E officer | Quarterly | HANWASH M&E officer | Quarterly
Outputs | 1120 | Train HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean.​ | 1120a | # of ambassadors who have completed training | - | people | In service - Needs training | Mattson | Training type, date, commune | Implementation event tracking form | PMO | After every training event | Implementation monitoring console |  |  | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Outputs | 1120 | Train HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean.​ | 1120b | # of coordinators who have completed training | - | people | In service - Needs training | Mattson | Training type, date, commune | Implementation event tracking form | PMO | After every training event | Implementation monitoring console |  |  | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Outputs | 1120 | Train HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean.​ | 1120c | # of training materials created in alignment with HANWASH three pillars and core values | - | Training materials | Not started | Mattson | Training type | Implementation event tracking form | PMO | Annually | Implementation monitoring console | Review of existing data | HANWASH M&E officer | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console
Outputs | 1120 | Train HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean.​ | 1120d | # of hours of training received by the HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean | Number of hours and number of people attending | Hours of training | Not started | Mattson | Training type | Implementation event tracking form | PMO | Quarterly | Implementation monitoring console | Review of existing data | Implementation monitoring console | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console
Immediate outcome | 1200 | Improved commune WASH planning and coordination by local authorities.​ | 1200a | % of approved interventions implemented in alignment with Commune Action Plans | "...in alignment with Commune Action Plans": -The activity was originally a part of a commune action plan, then implemented as part of a HANWASH project. | % of implemented activities | In service - Needs mods | Mattson | Date, commune | HANWASH project monitoring | PMO | Annually | Project monitoring console | Commune action plan | Commune WASH committee | Review of existing data | HANWASH M&E officer | Quarterly | Project monitoring console | It's critical that "Activities" planned by HANWASH correspond to those in the commune action plan in the system.
Outputs | 1210 | Create or improve commune action plans that focus on water, sanitation and hygiene, and water resource management.​ | 1210a | # of communes with action plans that explicitly include each W,S,H,WRM aspect (water, sanitation, hygiene, water resources management) | - | communes | In service - Needs mods | Mattson | Date, commune | HANWASH project monitoring | PMO | Annually | Project monitoring console |  |  | Review of existing data | HANWASH M&E officer | Quarterly | Project monitoring console | System validation consists of an exhaustive desk review of reported data
Outputs | 1220 | Facilitate coordination meetings between commune WASH stakeholders. | 1220a | # of WASH planning and coordination events with DINEPA and municipal officials | - | events/month | In service - Needs training | Mattson | Event type, participant group, date, commune | Implementation event tracking form | PMO | After every joint event | Implementation monitoring console |  |  | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Immediate outcome | 1300 | Improved accountability of service providers to users of WASH services.​ | 1300a | % of service providers under HANWASH initiative monitored according to national guidelines | "National guidelines:" -Water points: 1 x water survey per year -Piped water systems: 1 x Monthly Report per month | % of service providers in intervention communes | In service - Needs mods | Mattson | Water point/system, date, commune | Water point survey and SAEP monthly report | PMO | Water point: Annually Water system: Monthly" | Implementation monitoring console |  |  | Water point survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Immediate outcome | 1300 | Improved accountability of service providers to users of WASH services.​ | 1300b | % of intervention service providers with accountability structures in place | "Accountability structures in place": 1) Committee meets regularly 2) Committee meets with community regularly 3) Committee bylaws in place 4) Fees are collected 5) Records are available; 6) Reports are submitted to OREPA and the local authorities on a monthly basis | % of intervention water points | In service - Needs mods | Mattson | Water point, date, commune | Water point survey | PMO | On completion + annually | Implementation monitoring console | Water point survey |  | Water point survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Immediate outcome | 1300 | Improved accountability of service providers to users of WASH services.​ | 1300c | % of users being satisfied with the quality, affordability and reliability of the WASH services provided | This indicator measures the proportion of the households connected to the water system which are satisfied with the quality, affordability and reliability of the WASH services provided | % of households connected to the water systems | Not started | Mattson | Water point, commune | Household survey | PMO | On completion + annually | Implementation monitoring console | Water point survey - Audit | Third party contractor | Review of existing data | HANWASH M&E Officer | Annually | Implementation monitoring console
Outputs | 1310 | Monitor WASH service performance and satisfaction. | 1310a | # of intervention water systems regularly reporting data | "Regularly reporting data": 1) Submitted their monthly report | water systems | In service - Needs training | Mattson | Date, commune | Implementation event tracking form | PMO | After every training event | Implementation monitoring console |  |  | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Outputs | 1310 | Monitor WASH service performance and satisfaction. | 1310b | % of customer complaints resolved during the month | "Percent of complaints": 100 x # of complaints resolved during the month / # of complaints identified during the month | % of complaints | In service - Needs training | Mattson | Water system, date, commune | SAEP monthly report | Water service provider | Monthly | Implementation monitoring console | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Outputs | 1310 | Monitor WASH service performance and satisfaction. | 1310c | Average response time to resolve customer complaints | This indicator measures how long it takes on average for the service providers to resolve customer complaints. | Days | Not started | Mattson | Water system, date, commune | SAEP monthly report, Implementation Event tracking, Service Provider Monitoring form | Water service provider | Monthly | Implementation monitoring console |  |  | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Outputs | 1320 | Review service provider performance with stakeholders. | 1320a | # of communes which have held an annual service provider review with key stakeholders in the last year | Key stakeholders: Commune commitee, users, service providers, implementing partners | communes | In service - Needs mods | Mattson | Water system, date, commune | SAEP monthly report | Water service provider | Monthly | Implementation monitoring console |  |  | - | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Intermediate outcome | 2000 | Enhanced household access to and use of sustainable, affordable, and safe water, sanitation and hygiene services.​ | - | - | - | - | - | Mattson | - | - | - | - | - | - | - | - | - | - | - | This objective is split into its component objectives and measured via their indicators
Immediate outcome | 2100 | Increased household access to sustainable, affordable, and safe drinking water services.​ | 2100a | % of intervention water points which are functioning and potable | "Functioning": 1a) Functional: Water point is in good working condition and regularly provides water according the specifications in the original design. OR 1b) Partially functional but in need of repair: Water point provides water on a regular basis (possibly in a reduced capacity) but repairs are needed due to some maintenance issue or change in conditions at the site. Potable: 2) Free from E. Coli and priority contaminants | % of intervention water points | In service - Needs training | Mattson | Date, commune | Water point survey | PMO | On completion + annually | Implementation monitoring console |  |  | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Immediate outcome | 2100 | Increased household access to sustainable, affordable, and safe drinking water services.​ | 2100b | % of population in intervention communes with at least basic drinking water service | "...at least basic drinking water service": 1) Improved water source 2) Within 30 min round trip Note: This also includes basic and safely managed water service. | % of people in the commune | In service - Needs training | Mattson | Community, date, commune, improved water source, within 30 min round trip | Household WASH survey | PMO | On completion + annually | Implementation monitoring console |  |  | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Immediate outcome | 2100 | Increased household access to sustainable, affordable, and safe drinking water services.​ | 2100c | % of population in intervention communes with safely managed drinking water service | "Safely managed drinking water service": 1) Improved water source 2) Accessible on premises 3) Available when needed 4) Free from E. Coli and priority contaminants | % of people in the commune | In service - Needs training | Mattson | Community, date, commune, Improved water source, accessible on premises, available when needed, free from E. Coli and priority contaminants | Household WASH survey | PMO | On completion + annually | Implementation monitoring console |  |  | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Immediate outcome | 2100 | Increased household access to sustainable, affordable, and safe drinking water services.​ | 2100d | % of intervention water points which are functional, potable, and have a balanced budget or a budget with surplus after 2 years | 1a) Functional: Water point is in good working condition and regularly provides water according the specifications in the original design. OR 1b) Partially functional but in need of repair: Water point provides water on a regular basis (possibly in a reduced capacity) but repairs are needed due to some maintenance issue or change in conditions at the site. 2) "Potable": Free from E. Coli and priority contaminants. 3) "have a balanced budget": Monthly revenue excceeds expenses. 4) "after 2 years": Two years from the inauguration date. | % of intervention water points | In service - Needs mods | Mattson | Date, commune | Water point survey | PMO | On completion + annually | Implementation monitoring console |  |  | Water point survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Outputs | 2110 | Develop community managed water points. | 2110a | # of people in intervention communes with access to basic drinking water service through community managed water points | "Basic drinking water service": 1) Improved water source 2) Within 30 min round trip 3) [Household level] | people | In service - Needs training | Mattson | Water point, gender, age category, improved water source, within 30 min round trip | Water point survey | PMO | On completion | Implementation monitoring console |  |  | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Outputs | 2110 | Develop community managed water points. | 2110b | # of community managed water points created | "Community managed water points": 1) Signed CPE statutes with DINEPA | water points | In service - Needs training | Mattson | Date, commune | Implementation event tracking form | PMO | On completion | Implementation monitoring console |  |  | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Outputs | 2110 | Develop community managed water points. | 2110c | % of the community managed water points created which submit report to local authorities on a monthly basis | "Community managed water points": 1) Signed CPE statutes with DINEPA | water points | In service - Needs training | Mattson | Date, commune | Implementation event tracking form | PMO | Monthly | Implementation monitoring console | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Outputs | 2120 | Rehabilitate and expand professionally operated piped water systems. | 2120a | # of people added to safely managed drinking water service | "Safely managed drinking water service": 1) Improved water source 2) Available on premises 3) Available when needed 4) Free from E. Coli and priority contaminants | people | In service - Needs training | Mattson | Water point, gender, age category, improved water source, available on premises, available when needed, free from E. Coli and priority contaminants | SAEP monthly report | PMO | On completion | Implementation monitoring console |  |  | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Outputs | 2120 | Rehabilitate and expand professionally operated piped water systems. | 2120c | # of professionally managed piped water systems rehabilitated in the intervention communes | "Professionally managed water systems": 1) Signed OP statutes with DINEPA; Rehabilitated means: "The term "rehabilitated" implies that there was a pre-existing water supply system that may have been damaged, degraded, or in need of upgrades, and efforts were made to restore or enhance its functionality." | water systems | In service/Needs mods | Mattson | Water system, Date, commune | Implementation event tracking form | PMO | On completion | Implementation monitoring console | Household survey - Audit | Third party contractor | Review of existing data | Third party audit console (TBD) | Every two years
Outputs | 2120 | Rehabilitate and expand professionally operated piped water systems. | 2120b | # of professionally managed piped water systems created in the intervention communes | "Professionally managed water systems": 1) Signed OP statutes with DINEPA | water systems | In service/Needs mods | Mattson | Date, commune | Implementation event tracking form | PMO | On completion | Implementation monitoring console |  |  | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Immediate outcome | 2200 | Increased household access to sustainable, affordable, and safe sanitation services.​ | 2200a | % of intervention communities which are verified ODF | "Verified ODF": 0) [Verification conducted by commune WASH committee] 1) 100% of households have a toilet that has been used at least once 2) Toilets meet the minimum standards of hygiene, privacy, and security 3) Areas of defecation identified during contact visits, reported no evidence of fecal matter 4) Schools attended by 80% of children comply with health standards 5) Main market frequented by the population has a usable sanitary block or a formal step has been undertaken for this purpose 6) There is a willingness of the locality to maintain a state of ODF | % of intervention communities | In service - Needs training | Mattson | Date, commune | ODF verification and certification | PMO | On completion | Implementation monitoring console |  |  | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Immediate outcome | 2200 | Increased household access to sustainable, affordable, and safe sanitation services.​ | 2200b | % of population in intervention communes with at least basic sanitation service | "...at least basic sanitation service": Basic 1) Improved 2) Unshared 3) [Household level] Note: Includes basic and safely managed sanitation service. | % of people in the commune | In service/Needs mods | Mattson | Gender, age category, date, commune | Household WASH survey | PMO | Launch + verification + certification | Implementation monitoring console |  |  | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Immediate outcome | 2200 | Increased household access to sustainable, affordable, and safe sanitation services.​ | 2200c | % of population in intervention communes with safely managed sanitation service | "Safely managed sanitation service": 1) Improved 2) Unshared AND 3a) Excretia treated in situ OR 3b) Excretia emptied, transported, and treated | % of people in the commune | In service/Needs mods | Mattson | Gender, age category, date, commune | Household WASH survey | PMO | Launch + verification + certification | Implementation monitoring console |  |  | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Outputs | 2210 | Mobilize communities to achieve Open Defecation Free status | 2210a | # of people added to basic sanitation service in the intervention communes | "Basic sanitation service": 1) Improved 2) Unshared 3) [Household level] | people | In service/Needs mods | Mattson | Gender, age category, date, commune | Household WASH survey | PMO | On completion | Implementation monitoring console |  |  | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Outputs | 2210 | Mobilize communities to achieve Open Defecation Free status | 2210b | # of "intervention" communities verified ODF | "Verified ODF": 0) [Verification conducted by commune WASH committee] 1) 100% of households have a toilet that has been used at least once 2) Toilets meet the minimum standards of hygiene, privacy, and security 3) Areas of defecation identified during contact visits, reported no evidence of fecal matter 4) Schools attended by 80% of children comply with health standards 5) Main market frequented by the population has a usable sanitary block or a formal step has been undertaken for this purpose 6) There is a willingness of the locality to maintain a state of ODF | communities | In service/Needs mods | Mattson | Community, date, commune | ODF verification and certification | Commune WASH committee | On completion | Implementation monitoring console |  |  | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Outputs | 2220 | Certify the sustained usage of sanitation services. | 2220a | # of "intervention" communities certified ODF | "Certified ODF": 0) [Certification conducted by commune WASH committee] 1) Maintained "Verified ODF" criteria (see below) for at least 1 year. "Verified ODF": 0) [Verification conducted by commune WASH committee] 1) 100% of households have a toilet that has been used at least once 2) Toilets meet the minimum standards of hygiene, privacy, and security 3) Areas of defecation identified during contact visits, reported no evidence of fecal matter 4) Schools attended by 80% of children comply with health standards 5) Main market frequented by the population has a usable sanitary block or a formal step has been undertaken for this purpose 6) There is a willingness of the locality to maintain a state of ODF | communities | In service - Needs training | Mattson | Community, date, commune | ODF verification and certification | Commune WASH committee | Annually | Implementation monitoring console |  |  | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Outputs | 2230 | Construct public latrines. | 2230a | # of public latrines constructed | - | toilet blocks | In service - Needs training | HANWASH - Master | Community, date, commune | - | PMO | On completion | Implementation monitoring console |  |  | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | IT IS UNCLEAR HOW THIS FITS INTO HANWASH'S VISION. HOW ARE THESE TOILET BLOCKS MANAGED? IF IT IS A "CASA", THEN THEY CAN BE MANAGED AS ODF COMMUNITIES INSTEAD OF STANDALONE TOILET BLOCKS.
Immediate outcome | 2300 | Increased household access to hygiene services. | 2300a | % of population in intervention communes with at least basic hygiene service | "...at least basic hygiene service": 1) Presence of a Hanwashing facility on premises 2) Presence of soap and water | % of people within intervention communities | In service - Needs mods | Mattson | Gender, age category | Household WASH survey | PMO | Launch + verification + certification | Implementation monitoring console |  |  | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The Household survey - Audit is more detailed and precise, but it is a sampled check on the reporting system
Immediate outcome | 2300 | Increased household access to hygiene services. | 2300b | % of population in intervention communes with basic hygiene service | "Basic hygiene service": 1) Presence of a Hanwashing facility on premises 2) Presence of soap and water | % of people in the commune | In service - Needs mods | Mattson | Gender, age category | Household WASH survey | PMO | Launch + verification + certification | Implementation monitoring console |  |  | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The Household survey - Audit is more detailed and precise, but it is a sampled check on the reporting system
Outputs | 2310 | Train skilled community animators to deliver hygiene trainings and community mobilization.​ | 2310a | # of community animators trained | - | animators | In service - Needs mods | Mattson | Date, commune | Implementation event tracking form | PMO | After every training event | Implementation monitoring console |  |  | Review of existing data | Third party contractor | Every two years | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Outputs | 2310 | Train skilled community animators to deliver hygiene trainings and community mobilization.​ | 2310b | # of hours of hygiene trainings and community mobilization provided by the community animators trained | This indicator measures the intensity of the hygiene trainings and community mobilization delivered by the community animators. It is the sum of hours the community animator spends providing hygiene trainings. | Hours | Not started | Mattson | Date, commune, communities | Implementation event tracking form | PMO | After every training event | Implementation monitoring console | Review of existing data | Third party contractor | Review of existing data | HANWASH M&E officer | System validation consists of a sampled desk review of reported data | Implementation monitoring console
Outputs | 2320 | Certify the sustained usage of hygiene services. | 2320a | # of people added to basic hygiene service | "Basic hygiene service": 1) Presence of a facility 2) Presence of soap and water 3) [Household level] | people | In service - Needs mods | Mattson | Date, commune | ODF verification and certification | PMO | After every training event | Implementation monitoring console |  |  | Review of existing data | Third party contractor | Every two years | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Immediate outcome | 2400 | Increased access to sustainable, safe drinking water, sanitation, and hygiene materials in healthcare facilities, schools, and public places. | 2400a | % of schools with basic drinking water, sanitation, and hygiene services | "Basic drinking water service": 1) Improved 2) Currently available "Basic sanitation service": 1) Improved 2) Usable 3) Single sex toilets available "Basic hygiene service": 1) Presence of handwashing facilities 2) Presence of soap and water | % of intervention schools | In service - Needs training | HANWASH - Master | Water service level, sanitation service level, hygiene service level, date, commune | School WASH form | PMO | On completion + annually | Implementation monitoring console |  |  | School WASH form - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Immediate outcome | 2400 | Increased access to sustainable, safe drinking water, sanitation, and hygiene materials in healthcare facilities, schools, and public places. | 2400b | % of healthcare facilities with basic drinking water, sanitation, and hygiene services | "Basic drinking water service": 1) Improved 2) On premises 3) Currently available "Basic sanitation service": 1) Improved 2) Usable 3) Dedicated for staff 4) Sex-separated with menstrual hygiene facilities 5) Accessible for users with limited mobility "Basic hygiene service": ...At points of care 1) Facilities present 2) Soap and water or alcohol based hand rub present ...At toilets 1) Within 5 m of toilets 2) Facilities present 3) Soap and water present | % of intervention schools | In service - Needs training | HANWASH - Master | Water service level, sanitation service level, hygiene service level, date, commune | Healthcare facility WASH form | PMO | On completion + annually | Implementation monitoring console |  |  | Healthcare facility WASH form - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Outputs | 2410 | Construct or rehabilitate water supply for healthcare facilities and schools. | 2410a | # of schools added with basic drinking water services | "Basic drinking water service": 1) Improved 2) Currently available | schools | In service - Needs training | HANWASH - Master | Water service level, date, commune | School WASH form | PMO | On completion + annually | Implementation monitoring console |  |  | School WASH form - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Outputs | 2410 | Construct or rehabilitate water supply for healthcare facilities and schools. | 2410b | # of healthcare facilities added with basic drinking water services | "Basic drinking water service": 1) Improved 2) On premises 3) Currently available | healthcare facilities | In service - Needs training | HANWASH - Master | Water service level, date, commune | Healthcare facility WASH form | PMO | On completion + annually | Implementation monitoring console |  |  | Healthcare facility WASH form - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Outputs | 2420 | Construct communal, healthcare facility, and school latrines. | 2420a | # of schools added with basic sanitation services | "Basic sanitation service": 1) Improved 2) Usable 3) Single sex toilets available | schools | In service - Needs training | HANWASH - Master | Sanitation service level, date, commune | School WASH form | PMO | On completion + annually | Implementation monitoring console |  |  | School WASH form - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Outputs | 2420 | Construct communal, healthcare facility, and school latrines. | 2420b | # of healthcare facilities added with basic sanitation services | "Basic sanitation services": 1) Improved 2) Usable 3) Dedicated for staff 4) Sex-separated with menstrual hygiene facilities 5) Accessible for users with limited mobility | healthcare facilities | In service - Needs training | HANWASH - Master | Sanitation service level, date, commune | Healthcare facility WASH form | PMO | On completion + annually | Implementation monitoring console |  |  | Healthcare facility WASH form - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Outputs | 2430 | Work with (local authorities, civil society) to ensure access to soap or alcohol-based handrub at schools and healthcare facilities. | 2430a | # of schools added with basic hygiene | "Basic hygiene": 1) Presence of handwashing facilities 2) Presence of soap and water | schools | In service - Needs training | HANWASH - Master | Hygiene servicec level, date, commune | School WASH form | PMO | On completion + annually | Implementation monitoring console |  |  | School WASH form - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Outputs | 2430 | Work with (local authorities, civil society) to ensure access to soap or alcohol-based handrub at schools and healthcare facilities. | 2430b | # of healthcare facilities added with basic hygiene | "Basic hygiene": ...At points of care 1) Facilities present 2) Soap and water or alcohol based hand rub present ...At toilets 1) Within 5 m of toilets 2) Facilities present 3) Soap and water present | healthcare facilities | In service - Needs training | HANWASH - Master | Hygiene service level, date, commune | Healthcare facility WASH form | PMO | On completion + annually | Implementation monitoring console |  |  | Healthcare facility WASH form - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Intermediate outcome | 3000 | Expanded reach and resources leveraged through collective action with other national and international actors.​ | - | - | - | - | - | Mattson | - | - | - | - | - | - | - | - | - | - | - | This objective is split into its component objectives and measured via their indicators
Immediate outcome | 3100 | Increased government and non-government funding in alignment with HANWASH Core Values. | 3100a | Cumulative amount of money committed in alignment with HANWASH Core Values | Aligned with HANWASH Core Values: -### **LOCALLY LED** **We strengthen community participation in governance of WASH infrastructure and services.** ### **COLLABORATIVE** **Volunteers, government authorities, and partners are meaningfully engaged.** ### **** ### **SYSTEMATIC** **We will be thoughtful and consistent in planning, doing, and improving our work.** ### **IMPACTFUL** **Sustainability is a key metric of our success.** **** ### **COMMITTED** **We will not stop until the job is done.** | USD | In service | Mattson | Actor, project type date, commune | HANWASH project monitoring | HANWASH M&E Officer | Annually | Project monitoring console |  |  | Review of existing data | HANWASH M&E Officer & DINEPA | Annually | Project monitoring console | Since this indicator is completed by the HANWASH M&E officer, HANWASH should review the results with DINEPA as a check on the reporting system
Immediate outcome | 3100 | Increased government and non-government funding in alignment with HANWASH Core Values. | 3100b | % of committed money which has been spent (cumulative) | % spent (cumulative): (Cumulative_amount_spent / Cumulative_amount_committed) x 100 | % of amount committeed | In service - Needs training | Mattson | Commune, project, date | HANWASH project monitoring | HANWASH M&E Officer | Annually | Project monitoring console |  |  | Review of existing data | Third party contractor | Every two years | Third party audit console (TBD) | System validation consists of a sampled desk review of reported data
Outputs | 3110 | Mobilize and coordinate funding from government and non-government sources in HANWASH program areas in alignment with HANWASH Core Values. | 3110a | Amount of money spent by external actors within HANWASH project areas | Aligned with HANWASH Core Values: -### **LOCALLY LED** **We strengthen community participation in governance of WASH infrastructure and services.** ### **COLLABORATIVE** **Volunteers, government authorities, and partners are meaningfully engaged.** ### **** ### **SYSTEMATIC** **We will be thoughtful and consistent in planning, doing, and improving our work.** ### **IMPACTFUL** **Sustainability is a key metric of our success.** **** ### **COMMITTED** **We will not stop until the job is done.** | USD | In service | Mattson | Actor, date, commune | HANWASH project monitoring | HANWASH M&E Officer | Annually | Project monitoring console |  |  | Review of existing data | HANWASH M&E Officer & DINEPA | Annually | Project monitoring console | Since this indicator is completed by the HANWASH M&E officer, HANWASH should review the results with DINEPA as a check on the reporting system
Outputs | 3120 | Mobilize and influence funding from government and non-government sources beyond HANWASH program areas in alignment with HANWASH Core Values. | 3120a | Amount of money spent by external actors beyond project areas in alignment with HANWASH Core Values | Aligned with HANWASH Core Values: -### **LOCALLY LED** **We strengthen community participation in governance of WASH infrastructure and services.** ### **COLLABORATIVE** **Volunteers, government authorities, and partners are meaningfully engaged.** ### **** ### **SYSTEMATIC** **We will be thoughtful and consistent in planning, doing, and improving our work.** ### **IMPACTFUL** **Sustainability is a key metric of our success.** **** ### **COMMITTED** **We will not stop until the job is done.** | USD | In service | HANWASH - Master | Actor, date, commune | HANWASH project monitoring | HANWASH M&E Officer | Annually | Project monitoring console |  |  | Review of existing data | HANWASH M&E Officer & DINEPA | Annually | Project monitoring console | Since this indicator is completed by the HANWASH M&E officer, HANWASH should review the results with DINEPA as a check on the reporting system
Immediate outcome | 3200 | Increased capacity of DINEPA to regulate the sector and OREPA to oversee and support implementation. | 3200a | % of implementing partners in HANWASH program areas who have signed the DINEPA Accord Cadre | Number of IPs who have signed / Total number of IPs in HANWASH program areas x 100 | % of implementing partners in HANWASH program areas | In service - Needs mods | Mattson | Post/position, commune, department, date | SIEPA Accord Cadre | HANWASH M&E Officer | Annually | - | - | - | - | - | - | - | Since this information is contained in SIEPA, the HANWASH M&E Officer should work with ONEPA to aquire the data. Validation
Outputs | 3210 | Conduct leadership training of DINEPA and OREPA personnel. | 3210a | # of DINEPA personnel trained as leaders | - | people | In service - Needs training | Mattson | Gender, date, commune | Implementation event tracking form | PMO | After every training event | Implementation monitoring console |  |  | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Outputs | 3220 | Provide technical assistance and training to DINEPA and the OREPAs. | 3220a | # of technical trainings provided for DINEPA priority areas | Priorities areas for 2023-24: Unified national tariff methodology & ODF certification. | trainings | In service - Needs training | Mattson | Date, commune | Implementation event tracking form | PMO | After every assistance or training event | Implementation monitoring console |  |  | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Note on D11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Uniquely identifies each Indicator. The numerical part specifies the objective that it is measuring, and the alphabetical part allows there to be multiple indicators for a single objective.
Note on F11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This column contains definitions of any key terms in the description.
Note on G11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The unit used to provide context to the indicator value. For indicators measured as a percent, the Units specifies the denominator of the percent calculation e.g. % of intervention water points = (numerical indicator value)/(number of intervention water points)
Note on H11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In service: The data form has already been created and used previously. Needs mods: Some modification to the current data form may be necessary. Needs training: All of the appropriate stakeholders have not been trained on its usage.
Note on J11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These are the factors by which an indicator can be grouped (aggregation) or split into (disaggregation).
Note on Q11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The symbol "-", indicators that no new data collection is needed to validate this information.
Note on E14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: "Rotarian" includes: -Ambassador club members (within Haiti) -Champion club members (outside of Haiti) -HANWASH staff and volunteers M&E team, is this correct?
Note on E15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: "Rotarian" includes: -Ambassador club members (within Haiti) -Champion club members (outside of Haiti) -HANWASH staff and volunteers M&E team, is this correct? Reply: Set as row 14 Reply: I think this indicator is relevant since it assess, not only the participation but the extent to which Rotarians take the leadership of WASH events.
Note on E17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I think it's important to track the number of people reached by Rotarians in the commune events led by them. This can give us insights on the intensity of the advocacy efforts.
Note on E22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We replaced "implemented activities" with "approved interventions" to emphasize the fact that here we cannot talk about activities but interventions since in the CAP, intervention is used to described the different WASH products that need to be delivered at the commune level. "Approved" means that the interventions on which HANWASH or partners are working on should be assigned by local authorities to reinforce local leadership.
Note on E25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For more specificity, we added "...under HANWASH initiative…"
Note on F30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I believe it's important to measure this indicator to foster Service Providers' efficiency.
Note on E33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do we need to have this only after 2 yrs?
Note on E37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For more specificity in the indicator wording, I would suggest: "# of people in intervention communes with access to basic drinking water service through community managed water points"
Note on K39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We need to check if the Implementation Event Tracking form is suitable to register the CPE monthly reports. Otherwise, we'll need to create a specific form for those reports.
Note on E40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For more specificity in the indicator wording, I would suggest: "# of people in intervention communes with access to safely managed drinking water service through professionally operated piped water systems"
Note on E42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I added "...in the intervention communes" for more specificity.
Note on E46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: added "...in the intervention communities" for more specificity.
Note on E47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It would be less time consuming and more manageable to assess this for the communal sections. There are too many villages in the communes.
Note on E50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I replaced "people" by "population"
Note on E57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To make the indicator SMARTer, I would suggest this wording instead: "# of schools provided with access to basic drinking water services in the intervention communes"
Note on E58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To make the indicator SMARTer, I would suggest this wording instead: "# of healthcare facilities provided with access to basic drinking water services in the intervention communes"
Note on E59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To make the indicator SMARTer, I would suggest this wording instead: "# of schools provided with access to basic sanitation services in the intervention communes"
Note on E60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To make the indicator SMARTer, I would suggest this wording instead: "# of healthcare facilities provided with access to basic sanitation services in the intervention communes"
Note on E61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To make the indicator SMARTer, I would suggest this wording instead: "# of schools provided with access to basic hygiene services in the intervention communes"
Note on E62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To make the indicator SMARTer, I would suggest this wording instead: "# of healthcare facilities provided with access to basic hygiene services in the intervention communes"
Note on F64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need a definition for "Aligned with HANWASH Core Values" here
Note on E65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I would add "...in alignment with HANWASH goal, outcomes and Commune Action Plan"

## data
Type | Code | Description | Code_index | Indicator | Definitions | Units | Status | Program | (Dis)Aggregation | Source_link | Enumerator | Frequency_time | Visualization_link | Source | Validator | Frequency | Visualization | Notes
Ultimate outcome | 1 | Increased access to safe, sustainable and affordable water, sanitation and hygiene (WASH) services in Haiti​. | - | - | - | - | - | Mattson | - | - | - | - | - | - | - | - | - | This objective is split into its component objectives and measured via their indicators
Intermediate outcome | 1000 | Strengthened demand for and management of WASH services in communes. | - | - | - | - | - | Mattson | - | - | - | - | - | - | - | - | - | This objective is split into its component objectives and measured via their indicators
Immediate outcome | 1100 | Increased civil society engagement in decision making and implementation of WASH services. | 1100a | % of commune WASH events with Rotarian participation | - | % of commune level events reported | In service - Needs training | Mattson | Event type, participant group, date, commune | Implementation event tracking form | Rotary ambassadors | After every implementation event | Implementation monitoring console | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of an exhaustive desk review of both the PMO and Rotarians forms.
Immediate outcome | 1100 | Increased civil society engagement in decision making and implementation of WASH services. | 1100b | % of commune WASH events led by trained HANWASH Ambassadors and Coordinators to communicate WASH messages and advocate for HANWASH goal | "…led by Rotarians…" means the WASH activities whose initiative have been taken by Rotarians. | % of commune level WASH events reported | Not started | Mattson | Event type, participant group, date, commune | Implementation event tracking form | Rotary ambassadors | After every implementation event | Implementation monitoring console | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console
Outputs | 1110 | Support civil society engagement in the WASH sector.​ | 1110a | # of volunteer hours per month spent by Rotarians in WASH events |  | volunteer hours / club / month | In service - Needs training | Mattson | Event type, participant group, date, commune | Implementation event tracking form | Rotary ambassadors | After every implementation event | Implementation monitoring console | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of an exhaustive desk review of both the PMO and Rotarians forms.
Outputs | 1110 | Support civil society engagement in the WASH sector.​ | 1110b | Number of people reached by the HANWASH Ambassadors, Coordinators and Rotarians in general in the Commune WASH events and advocacy efforts led by them | "Number of people reached…": Number of people participating in the WASH events led by Rotarians. | people | In service - Needs training | Mattson | Event type, participant group, date, commune | Implementation event tracking form | Rotary ambassadors | After every implementation event | Implementation monitoring console | Quarterly | HANWASH M&E officer | Quarterly
Outputs | 1120 | Train HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean.​ | 1120a | # of ambassadors who have completed training | - | people | In service - Needs training | Mattson | Training type, date, commune | Implementation event tracking form | PMO | After every training event | Implementation monitoring console | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Outputs | 1120 | Train HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean.​ | 1120b | # of coordinators who have completed training | - | people | In service - Needs training | Mattson | Training type, date, commune | Implementation event tracking form | PMO | After every training event | Implementation monitoring console | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Outputs | 1120 | Train HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean.​ | 1120c | # of training materials created in alignment with HANWASH three pillars and core values | - | Training materials | Not started | Mattson | Training type | Implementation event tracking form | PMO | Annually | Implementation monitoring console | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console
Outputs | 1120 | Train HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean.​ | 1120d | # of hours of training received by the HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean | Number of hours and number of people attending | Hours of training | Not started | Mattson | Training type | Implementation event tracking form | PMO | Quarterly | Implementation monitoring console | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console
Immediate outcome | 1200 | Improved commune WASH planning and coordination by local authorities.​ | 1200a | % of approved interventions implemented in alignment with Commune Action Plans | "...in alignment with Commune Action Plans": -The activity was originally a part of a commune action plan, then implemented as part of a HANWASH project. | % of implemented activities | In service - Needs mods | Mattson | Date, commune | HANWASH project monitoring | PMO | Annually | Project monitoring console | Review of existing data | HANWASH M&E officer | Quarterly | Project monitoring console | It's critical that "Activities" planned by HANWASH correspond to those in the commune action plan in the system.
Outputs | 1210 | Create or improve commune action plans that focus on water, sanitation and hygiene, and water resource management.​ | 1210a | # of communes with action plans that explicitly include each W,S,H,WRM aspect (water, sanitation, hygiene, water resources management) | - | communes | In service - Needs mods | Mattson | Date, commune | HANWASH project monitoring | PMO | Annually | Project monitoring console | Review of existing data | HANWASH M&E officer | Quarterly | Project monitoring console | System validation consists of an exhaustive desk review of reported data
Outputs | 1220 | Facilitate coordination meetings between commune WASH stakeholders. | 1220a | # of WASH planning and coordination events with DINEPA and municipal officials | - | events/month | In service - Needs training | Mattson | Event type, participant group, date, commune | Implementation event tracking form | PMO | After every joint event | Implementation monitoring console | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Immediate outcome | 1300 | Improved accountability of service providers to users of WASH services.​ | 1300a | % of service providers under HANWASH initiative monitored according to national guidelines | "National guidelines:" -Water points: 1 x water survey per year -Piped water systems: 1 x Monthly Report per month | % of service providers in intervention communes | In service - Needs mods | Mattson | Water point/system, date, commune | Water point survey and SAEP monthly report | PMO | Water point: Annually Water system: Monthly" | Implementation monitoring console | Water point survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Immediate outcome | 1300 | Improved accountability of service providers to users of WASH services.​ | 1300b | % of intervention service providers with accountability structures in place | "Accountability structures in place": 1) Committee meets regularly 2) Committee meets with community regularly 3) Committee bylaws in place 4) Fees are collected 5) Records are available; 6) Reports are submitted to OREPA and the local authorities on a monthly basis | % of intervention water points | In service - Needs mods | Mattson | Water point, date, commune | Water point survey | PMO | On completion + annually | Implementation monitoring console | Water point survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Immediate outcome | 1300 | Improved accountability of service providers to users of WASH services.​ | 1300c | % of users being satisfied with the quality, affordability and reliability of the WASH services provided | This indicator measures the proportion of the households connected to the water system which are satisfied with the quality, affordability and reliability of the WASH services provided | % of households connected to the water systems | Not started | Mattson | Water point, commune | Household survey | PMO | On completion + annually | Implementation monitoring console | Review of existing data | HANWASH M&E Officer | Annually | Implementation monitoring console
Outputs | 1310 | Monitor WASH service performance and satisfaction. | 1310a | # of intervention water systems regularly reporting data | "Regularly reporting data": 1) Submitted their monthly report | water systems | In service - Needs training | Mattson | Date, commune | Implementation event tracking form | PMO | After every training event | Implementation monitoring console | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Outputs | 1310 | Monitor WASH service performance and satisfaction. | 1310b | % of customer complaints resolved during the month | "Percent of complaints": 100 x # of complaints resolved during the month / # of complaints identified during the month | % of complaints | In service - Needs training | Mattson | Water system, date, commune | SAEP monthly report | Water service provider | Monthly | Implementation monitoring console | Quarterly | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Outputs | 1310 | Monitor WASH service performance and satisfaction. | 1310c | Average response time to resolve customer complaints | This indicator measures how long it takes on average for the service providers to resolve customer complaints. | Days | Not started | Mattson | Water system, date, commune | SAEP monthly report, Implementation Event tracking, Service Provider Monitoring form | Water service provider | Monthly | Implementation monitoring console | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Intermediate outcome | 2000 | Enhanced household access to and use of sustainable, affordable, and safe water, sanitation and hygiene services.​ | - | - | - | - | - | Mattson | - | - | - | - | - | - | - | - | - | This objective is split into its component objectives and measured via their indicators
Immediate outcome | 2100 | Increased household access to sustainable, affordable, and safe drinking water services.​ | 2100a | % of intervention water points which are functioning and potable | "Functioning": 1a) Functional: Water point is in good working condition and regularly provides water according the specifications in the original design. OR 1b) Partially functional but in need of repair: Water point provides water on a regular basis (possibly in a reduced capacity) but repairs are needed due to some maintenance issue or change in conditions at the site. Potable: 2) Free from E. Coli and priority contaminants | % of intervention water points | In service - Needs training | Mattson | Date, commune | Water point survey | PMO | On completion + annually | Implementation monitoring console | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Immediate outcome | 2100 | Increased household access to sustainable, affordable, and safe drinking water services.​ | 2100b | % of population in intervention communes with at least basic drinking water service | "...at least basic drinking water service": 1) Improved water source 2) Within 30 min round trip Note: This also includes basic and safely managed water service. | % of people in the commune | In service - Needs training | Mattson | Community, date, commune, improved water source, within 30 min round trip | Household WASH survey | PMO | On completion + annually | Implementation monitoring console | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Immediate outcome | 2100 | Increased household access to sustainable, affordable, and safe drinking water services.​ | 2100c | % of population in intervention communes with safely managed drinking water service | "Safely managed drinking water service": 1) Improved water source 2) Accessible on premises 3) Available when needed 4) Free from E. Coli and priority contaminants | % of people in the commune | In service - Needs training | Mattson | Community, date, commune, Improved water source, accessible on premises, available when needed, free from E. Coli and priority contaminants | Household WASH survey | PMO | On completion + annually | Implementation monitoring console | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Immediate outcome | 2100 | Increased household access to sustainable, affordable, and safe drinking water services.​ | 2100d | % of intervention water points which are functional, potable, and have a balanced budget or a budget with surplus after 2 years | 1a) Functional: Water point is in good working condition and regularly provides water according the specifications in the original design. OR 1b) Partially functional but in need of repair: Water point provides water on a regular basis (possibly in a reduced capacity) but repairs are needed due to some maintenance issue or change in conditions at the site. 2) "Potable": Free from E. Coli and priority contaminants. 3) "have a balanced budget": Monthly revenue excceeds expenses. 4) "after 2 years": Two years from the inauguration date. | % of intervention water points | In service - Needs mods | Mattson | Date, commune | Water point survey | PMO | On completion + annually | Implementation monitoring console | Water point survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Outputs | 2110 | Develop community managed water points. | 2110a | # of people in intervention communes with access to basic drinking water service through community managed water points | "Basic drinking water service": 1) Improved water source 2) Within 30 min round trip 3) [Household level] | people | In service - Needs training | Mattson | Water point, gender, age category, improved water source, within 30 min round trip | Water point survey | PMO | On completion | Implementation monitoring console | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Outputs | 2110 | Develop community managed water points. | 2110b | # of community managed water points created | "Community managed water points": 1) Signed CPE statutes with DINEPA | water points | In service - Needs training | Mattson | Date, commune | Implementation event tracking form | PMO | On completion | Implementation monitoring console | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Outputs | 2110 | Develop community managed water points. | 2110c | % of the community managed water points created which submit report to local authorities on a monthly basis | "Community managed water points": 1) Signed CPE statutes with DINEPA | water points | In service - Needs training | Mattson | Date, commune | Implementation event tracking form | PMO | Monthly | Implementation monitoring console | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Outputs | 2120 | Rehabilitate and expand professionally operated piped water systems. | 2120a | # of people added to safely managed drinking water service | "Safely managed drinking water service": 1) Improved water source 2) Available on premises 3) Available when needed 4) Free from E. Coli and priority contaminants | people | In service - Needs training | Mattson | Water point, gender, age category, improved water source, available on premises, available when needed, free from E. Coli and priority contaminants | SAEP monthly report | PMO | On completion | Implementation monitoring console | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Outputs | 2120 | Rehabilitate and expand professionally operated piped water systems. | 2120c | # of professionally managed piped water systems rehabilitated in the intervention communes | "Professionally managed water systems": 1) Signed OP statutes with DINEPA; Rehabilitated means: "The term "rehabilitated" implies that there was a pre-existing water supply system that may have been damaged, degraded, or in need of upgrades, and efforts were made to restore or enhance its functionality." | water systems | In service/Needs mods | Mattson | Water system, Date, commune | Implementation event tracking form | PMO | On completion | Implementation monitoring console | Review of existing data | Third party audit console (TBD) | Every two years
Outputs | 2120 | Rehabilitate and expand professionally operated piped water systems. | 2120b | # of professionally managed piped water systems created in the intervention communes | "Professionally managed water systems": 1) Signed OP statutes with DINEPA | water systems | In service/Needs mods | Mattson | Date, commune | Implementation event tracking form | PMO | On completion | Implementation monitoring console | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Immediate outcome | 2200 | Increased household access to sustainable, affordable, and safe sanitation services.​ | 2200a | % of intervention communities which are verified ODF | "Verified ODF": 0) [Verification conducted by commune WASH committee] 1) 100% of households have a toilet that has been used at least once 2) Toilets meet the minimum standards of hygiene, privacy, and security 3) Areas of defecation identified during contact visits, reported no evidence of fecal matter 4) Schools attended by 80% of children comply with health standards 5) Main market frequented by the population has a usable sanitary block or a formal step has been undertaken for this purpose 6) There is a willingness of the locality to maintain a state of ODF | % of intervention communities | In service - Needs training | Mattson | Date, commune | ODF verification and certification | PMO | On completion | Implementation monitoring console | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Immediate outcome | 2200 | Increased household access to sustainable, affordable, and safe sanitation services.​ | 2200b | % of population in intervention communes with at least basic sanitation service | "...at least basic sanitation service": Basic 1) Improved 2) Unshared 3) [Household level] Note: Includes basic and safely managed sanitation service. | % of people in the commune | In service/Needs mods | Mattson | Gender, age category, date, commune | Household WASH survey | PMO | Launch + verification + certification | Implementation monitoring console | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Immediate outcome | 2200 | Increased household access to sustainable, affordable, and safe sanitation services.​ | 2200c | % of population in intervention communes with safely managed sanitation service | "Safely managed sanitation service": 1) Improved 2) Unshared AND 3a) Excretia treated in situ OR 3b) Excretia emptied, transported, and treated | % of people in the commune | In service/Needs mods | Mattson | Gender, age category, date, commune | Household WASH survey | PMO | Launch + verification + certification | Implementation monitoring console | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Outputs | 2210 | Mobilize communities to achieve Open Defecation Free status | 2210a | # of people added to basic sanitation service in the intervention communes | "Basic sanitation service": 1) Improved 2) Unshared 3) [Household level] | people | In service/Needs mods | Mattson | Gender, age category, date, commune | Household WASH survey | PMO | On completion | Implementation monitoring console | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Outputs | 2210 | Mobilize communities to achieve Open Defecation Free status | 2210b | # of "intervention" communities verified ODF | "Verified ODF": 0) [Verification conducted by commune WASH committee] 1) 100% of households have a toilet that has been used at least once 2) Toilets meet the minimum standards of hygiene, privacy, and security 3) Areas of defecation identified during contact visits, reported no evidence of fecal matter 4) Schools attended by 80% of children comply with health standards 5) Main market frequented by the population has a usable sanitary block or a formal step has been undertaken for this purpose 6) There is a willingness of the locality to maintain a state of ODF | communities | In service/Needs mods | Mattson | Community, date, commune | ODF verification and certification | Commune WASH committee | On completion | Implementation monitoring console | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Outputs | 2220 | Certify the sustained usage of sanitation services. | 2220a | # of "intervention" communities certified ODF | "Certified ODF": 0) [Certification conducted by commune WASH committee] 1) Maintained "Verified ODF" criteria (see below) for at least 1 year. "Verified ODF": 0) [Verification conducted by commune WASH committee] 1) 100% of households have a toilet that has been used at least once 2) Toilets meet the minimum standards of hygiene, privacy, and security 3) Areas of defecation identified during contact visits, reported no evidence of fecal matter 4) Schools attended by 80% of children comply with health standards 5) Main market frequented by the population has a usable sanitary block or a formal step has been undertaken for this purpose 6) There is a willingness of the locality to maintain a state of ODF | communities | In service - Needs training | Mattson | Community, date, commune | ODF verification and certification | Commune WASH committee | Annually | Implementation monitoring console | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The system validation form is more detailed and precise, but it is a sampled check on the reporting system
Outputs | 2230 | Construct public latrines. | 2230a | # of public latrines constructed | - | toilet blocks | In service - Needs training | HANWASH - Master | Community, date, commune | - | PMO | On completion | Implementation monitoring console | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | IT IS UNCLEAR HOW THIS FITS INTO HANWASH'S VISION. HOW ARE THESE TOILET BLOCKS MANAGED? IF IT IS A "CASA", THEN THEY CAN BE MANAGED AS ODF COMMUNITIES INSTEAD OF STANDALONE TOILET BLOCKS.
Immediate outcome | 2300 | Increased household access to hygiene services. | 2300a | % of population in intervention communes with at least basic hygiene service | "...at least basic hygiene service": 1) Presence of a Hanwashing facility on premises 2) Presence of soap and water | % of people within intervention communities | In service - Needs mods | Mattson | Gender, age category | Household WASH survey | PMO | Launch + verification + certification | Implementation monitoring console | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The Household survey - Audit is more detailed and precise, but it is a sampled check on the reporting system
Immediate outcome | 2300 | Increased household access to hygiene services. | 2300b | % of population in intervention communes with basic hygiene service | "Basic hygiene service": 1) Presence of a Hanwashing facility on premises 2) Presence of soap and water | % of people in the commune | In service - Needs mods | Mattson | Gender, age category | Household WASH survey | PMO | Launch + verification + certification | Implementation monitoring console | Household survey - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The Household survey - Audit is more detailed and precise, but it is a sampled check on the reporting system
Outputs | 2310 | Train skilled community animators to deliver hygiene trainings and community mobilization.​ | 2310a | # of community animators trained | - | animators | In service - Needs mods | Mattson | Date, commune | Implementation event tracking form | PMO | After every training event | Implementation monitoring console | Review of existing data | Third party contractor | Every two years | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Outputs | 2310 | Train skilled community animators to deliver hygiene trainings and community mobilization.​ | 2310b | # of hours of hygiene trainings and community mobilization provided by the community animators trained | This indicator measures the intensity of the hygiene trainings and community mobilization delivered by the community animators. It is the sum of hours the community animator spends providing hygiene trainings. | Hours | Not started | Mattson | Date, commune, communities | Implementation event tracking form | PMO | After every training event | Implementation monitoring console | Review of existing data | HANWASH M&E officer | System validation consists of a sampled desk review of reported data | Implementation monitoring console
Outputs | 2320 | Certify the sustained usage of hygiene services. | 2320a | # of people added to basic hygiene service | "Basic hygiene service": 1) Presence of a facility 2) Presence of soap and water 3) [Household level] | people | In service - Needs mods | Mattson | Date, commune | ODF verification and certification | PMO | After every training event | Implementation monitoring console | Review of existing data | Third party contractor | Every two years | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Immediate outcome | 2400 | Increased access to sustainable, safe drinking water, sanitation, and hygiene materials in healthcare facilities, schools, and public places. | 2400a | % of schools with basic drinking water, sanitation, and hygiene services | "Basic drinking water service": 1) Improved 2) Currently available "Basic sanitation service": 1) Improved 2) Usable 3) Single sex toilets available "Basic hygiene service": 1) Presence of handwashing facilities 2) Presence of soap and water | % of intervention schools | In service - Needs training | HANWASH - Master | Water service level, sanitation service level, hygiene service level, date, commune | School WASH form | PMO | On completion + annually | Implementation monitoring console | School WASH form - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Immediate outcome | 2400 | Increased access to sustainable, safe drinking water, sanitation, and hygiene materials in healthcare facilities, schools, and public places. | 2400b | % of healthcare facilities with basic drinking water, sanitation, and hygiene services | "Basic drinking water service": 1) Improved 2) On premises 3) Currently available "Basic sanitation service": 1) Improved 2) Usable 3) Dedicated for staff 4) Sex-separated with menstrual hygiene facilities 5) Accessible for users with limited mobility "Basic hygiene service": ...At points of care 1) Facilities present 2) Soap and water or alcohol based hand rub present ...At toilets 1) Within 5 m of toilets 2) Facilities present 3) Soap and water present | % of intervention schools | In service - Needs training | HANWASH - Master | Water service level, sanitation service level, hygiene service level, date, commune | Healthcare facility WASH form | PMO | On completion + annually | Implementation monitoring console | Healthcare facility WASH form - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Outputs | 2410 | Construct or rehabilitate water supply for healthcare facilities and schools. | 2410a | # of schools added with basic drinking water services | "Basic drinking water service": 1) Improved 2) Currently available | schools | In service - Needs training | HANWASH - Master | Water service level, date, commune | School WASH form | PMO | On completion + annually | Implementation monitoring console | School WASH form - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Outputs | 2410 | Construct or rehabilitate water supply for healthcare facilities and schools. | 2410b | # of healthcare facilities added with basic drinking water services | "Basic drinking water service": 1) Improved 2) On premises 3) Currently available | healthcare facilities | In service - Needs training | HANWASH - Master | Water service level, date, commune | Healthcare facility WASH form | PMO | On completion + annually | Implementation monitoring console | Healthcare facility WASH form - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Outputs | 2420 | Construct communal, healthcare facility, and school latrines. | 2420a | # of schools added with basic sanitation services | "Basic sanitation service": 1) Improved 2) Usable 3) Single sex toilets available | schools | In service - Needs training | HANWASH - Master | Sanitation service level, date, commune | School WASH form | PMO | On completion + annually | Implementation monitoring console | School WASH form - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Outputs | 2420 | Construct communal, healthcare facility, and school latrines. | 2420b | # of healthcare facilities added with basic sanitation services | "Basic sanitation services": 1) Improved 2) Usable 3) Dedicated for staff 4) Sex-separated with menstrual hygiene facilities 5) Accessible for users with limited mobility | healthcare facilities | In service - Needs training | HANWASH - Master | Sanitation service level, date, commune | Healthcare facility WASH form | PMO | On completion + annually | Implementation monitoring console | Healthcare facility WASH form - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Outputs | 2430 | Work with (local authorities, civil society) to ensure access to soap or alcohol-based handrub at schools and healthcare facilities. | 2430a | # of schools added with basic hygiene | "Basic hygiene": 1) Presence of handwashing facilities 2) Presence of soap and water | schools | In service - Needs training | HANWASH - Master | Hygiene servicec level, date, commune | School WASH form | PMO | On completion + annually | Implementation monitoring console | School WASH form - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Outputs | 2430 | Work with (local authorities, civil society) to ensure access to soap or alcohol-based handrub at schools and healthcare facilities. | 2430b | # of healthcare facilities added with basic hygiene | "Basic hygiene": ...At points of care 1) Facilities present 2) Soap and water or alcohol based hand rub present ...At toilets 1) Within 5 m of toilets 2) Facilities present 3) Soap and water present | healthcare facilities | In service - Needs training | HANWASH - Master | Hygiene service level, date, commune | Healthcare facility WASH form | PMO | On completion + annually | Implementation monitoring console | Healthcare facility WASH form - Audit | Third party contractor | Every two years | Third party audit console (TBD) | The reporting and system validation forms are the same, just different deployments carried out by different stakeholders. Reporting: PMO. Validation: Third party contractor.
Intermediate outcome | 3000 | Expanded reach and resources leveraged through collective action with other national and international actors.​ | - | - | - | - | - | Mattson | - | - | - | - | - | - | - | - | - | This objective is split into its component objectives and measured via their indicators
Immediate outcome | 3100 | Increased government and non-government funding in alignment with HANWASH Core Values. | 3100a | Cumulative amount of money committed in alignment with HANWASH Core Values | Aligned with HANWASH Core Values: -### **LOCALLY LED** **We strengthen community participation in governance of WASH infrastructure and services.** ### **COLLABORATIVE** **Volunteers, government authorities, and partners are meaningfully engaged.** ### **** ### **SYSTEMATIC** **We will be thoughtful and consistent in planning, doing, and improving our work.** ### **IMPACTFUL** **Sustainability is a key metric of our success.** **** ### **COMMITTED** **We will not stop until the job is done.** | USD | In service | Mattson | Actor, project type date, commune | HANWASH project monitoring | HANWASH M&E Officer | Annually | Project monitoring console | Review of existing data | HANWASH M&E Officer & DINEPA | Annually | Project monitoring console | Since this indicator is completed by the HANWASH M&E officer, HANWASH should review the results with DINEPA as a check on the reporting system
Immediate outcome | 3100 | Increased government and non-government funding in alignment with HANWASH Core Values. | 3100b | % of committed money which has been spent (cumulative) | % spent (cumulative): (Cumulative_amount_spent / Cumulative_amount_committed) x 100 | % of amount committeed | In service - Needs training | Mattson | Commune, project, date | HANWASH project monitoring | HANWASH M&E Officer | Annually | Project monitoring console | Review of existing data | Third party contractor | Every two years | Third party audit console (TBD) | System validation consists of a sampled desk review of reported data
Outputs | 3110 | Mobilize and coordinate funding from government and non-government sources in HANWASH program areas in alignment with HANWASH Core Values. | 3110a | Amount of money spent by external actors within HANWASH project areas | Aligned with HANWASH Core Values: -### **LOCALLY LED** **We strengthen community participation in governance of WASH infrastructure and services.** ### **COLLABORATIVE** **Volunteers, government authorities, and partners are meaningfully engaged.** ### **** ### **SYSTEMATIC** **We will be thoughtful and consistent in planning, doing, and improving our work.** ### **IMPACTFUL** **Sustainability is a key metric of our success.** **** ### **COMMITTED** **We will not stop until the job is done.** | USD | In service | Mattson | Actor, date, commune | HANWASH project monitoring | HANWASH M&E Officer | Annually | Project monitoring console | Review of existing data | HANWASH M&E Officer & DINEPA | Annually | Project monitoring console | Since this indicator is completed by the HANWASH M&E officer, HANWASH should review the results with DINEPA as a check on the reporting system
Outputs | 3120 | Mobilize and influence funding from government and non-government sources beyond HANWASH program areas in alignment with HANWASH Core Values. | 3120a | Amount of money spent by external actors beyond project areas in alignment with HANWASH Core Values | Aligned with HANWASH Core Values: -### **LOCALLY LED** **We strengthen community participation in governance of WASH infrastructure and services.** ### **COLLABORATIVE** **Volunteers, government authorities, and partners are meaningfully engaged.** ### **** ### **SYSTEMATIC** **We will be thoughtful and consistent in planning, doing, and improving our work.** ### **IMPACTFUL** **Sustainability is a key metric of our success.** **** ### **COMMITTED** **We will not stop until the job is done.** | USD | In service | HANWASH - Master | Actor, date, commune | HANWASH project monitoring | HANWASH M&E Officer | Annually | Project monitoring console | Review of existing data | HANWASH M&E Officer & DINEPA | Annually | Project monitoring console | Since this indicator is completed by the HANWASH M&E officer, HANWASH should review the results with DINEPA as a check on the reporting system
Immediate outcome | 3200 | Increased capacity of DINEPA to regulate the sector and OREPA to oversee and support implementation. | 3200a | % of implementing partners in HANWASH program areas who have signed the DINEPA Accord Cadre | Number of IPs who have signed / Total number of IPs in HANWASH program areas x 100 | % of implementing partners in HANWASH program areas | In service - Needs mods | Mattson | Post/position, commune, department, date | SIEPA Accord Cadre | HANWASH M&E Officer | Annually | - | - | - | - | - | Since this information is contained in SIEPA, the HANWASH M&E Officer should work with ONEPA to aquire the data. Validation
Outputs | 3210 | Conduct leadership training of DINEPA and OREPA personnel. | 3210a | # of DINEPA personnel trained as leaders | - | people | In service - Needs training | Mattson | Gender, date, commune | Implementation event tracking form | PMO | After every training event | Implementation monitoring console | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Outputs | 3220 | Provide technical assistance and training to DINEPA and the OREPAs. | 3220a | # of technical trainings provided for DINEPA priority areas | Priorities areas for 2023-24: Unified national tariff methodology & ODF certification. | trainings | In service - Needs training | Mattson | Date, commune | Implementation event tracking form | PMO | After every assistance or training event | Implementation monitoring console | Review of existing data | HANWASH M&E officer | Quarterly | Implementation monitoring console | System validation consists of a sampled desk review of reported data
Note on D1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Uniquely identifies each Indicator. The numerical part specifies the objective that it is measuring, and the alphabetical part allows there to be multiple indicators for a single objective.
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This column contains definitions of any key terms in the description.
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The unit used to provide context to the indicator value. For indicators measured as a percent, the Units specifies the denominator of the percent calculation e.g. % of intervention water points = (numerical indicator value)/(number of intervention water points)
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In service: The data form has already been created and used previously. Needs mods: Some modification to the current data form may be necessary. Needs training: All of the appropriate stakeholders have not been trained on its usage.
Note on J1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These are the factors by which an indicator can be grouped (aggregation) or split into (disaggregation).
Note on O1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The symbol "-", indicators that no new data collection is needed to validate this information.
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: "Rotarian" includes: -Ambassador club members (within Haiti) -Champion club members (outside of Haiti) -HANWASH staff and volunteers M&E team, is this correct?
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: "Rotarian" includes: -Ambassador club members (within Haiti) -Champion club members (outside of Haiti) -HANWASH staff and volunteers M&E team, is this correct? Reply: Set as row 14 Reply: I think this indicator is relevant since it assess, not only the participation but the extent to which Rotarians take the leadership of WASH events.
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I think it's important to track the number of people reached by Rotarians in the commune events led by them. This can give us insights on the intensity of the advocacy efforts.
Note on E12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We replaced "implemented activities" with "approved interventions" to emphasize the fact that here we cannot talk about activities but interventions since in the CAP, intervention is used to described the different WASH products that need to be delivered at the commune level. "Approved" means that the interventions on which HANWASH or partners are working on should be assigned by local authorities to reinforce local leadership.
Note on E15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For more specificity, we added "...under HANWASH initiative…"
Note on F20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I believe it's important to measure this indicator to foster Service Providers' efficiency.
Note on E22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do we need to have this only after 2 yrs?
Note on E26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For more specificity in the indicator wording, I would suggest: "# of people in intervention communes with access to basic drinking water service through community managed water points"
Note on K28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We need to check if the Implementation Event Tracking form is suitable to register the CPE monthly reports. Otherwise, we'll need to create a specific form for those reports.
Note on E29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For more specificity in the indicator wording, I would suggest: "# of people in intervention communes with access to safely managed drinking water service through professionally operated piped water systems"
Note on E31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I added "...in the intervention communes" for more specificity.
Note on E35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: added "...in the intervention communities" for more specificity.
Note on E36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It would be less time consuming and more manageable to assess this for the communal sections. There are too many villages in the communes.
Note on E39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I replaced "people" by "population"
Note on E46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To make the indicator SMARTer, I would suggest this wording instead: "# of schools provided with access to basic drinking water services in the intervention communes"
Note on E47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To make the indicator SMARTer, I would suggest this wording instead: "# of healthcare facilities provided with access to basic drinking water services in the intervention communes"
Note on E48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To make the indicator SMARTer, I would suggest this wording instead: "# of schools provided with access to basic sanitation services in the intervention communes"
Note on E49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To make the indicator SMARTer, I would suggest this wording instead: "# of healthcare facilities provided with access to basic sanitation services in the intervention communes"
Note on E50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To make the indicator SMARTer, I would suggest this wording instead: "# of schools provided with access to basic hygiene services in the intervention communes"
Note on E51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To make the indicator SMARTer, I would suggest this wording instead: "# of healthcare facilities provided with access to basic hygiene services in the intervention communes"
Note on F53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need a definition for "Aligned with HANWASH Core Values" here
Note on E54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I would add "...in alignment with HANWASH goal, outcomes and Commune Action Plan"

## Performance objectives
Organization: HANWASH
Document: Performance objectives framework
Objective: Establish a structure for reporting key milestones to high-level stakeholders
Scope: Mattson Program
Reference link: TBD
Version number: 2.41
Version date: March 21, 2024
Performance Objectives Framework
Category |  |  | Indicator |  | Indicative Targets (subject to change as we collect baseline data)
# | Name | Objective | ID | Name | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
1 | Localization | Improved commune WASH planning and coordination by local authorities.​ | 1200a | % of approved interventions implemented in alignment with Commune Action Plans | Commune Action Plans are finalized as necessary | 10% | 20% | 40% | 90% of activities | "Approved interventions" means the specific interventions from the Commune Action Plans which are assigned to HANWASH by the Mayor's Offices.
2 | Systematization | Improved accountability of service providers to users of WASH services.​ | 1300a | % of service providers under HANWASH initiative monitored according to national guidelines | mWater platform fully operational | 10% | 20% | 50% | 100% of service providers | 90% looks more realistic for year 5. Maybe we should have the same percentages.
3 | Impact | Enhanced household access to and use of sustainable, affordable, and safe water, sanitation and hygiene services.​ | 2100b 2200b 2300b | -% of population in intervention communes with at least basic drinking water service -...basic sanitation service -...basic hygiene service | Baseline study carried out and documented | 2 pct* points | 5 pct points | 10 pct points | Current + 20% (100,000 people) | More realistic to say: 5%, 9%, 15% and then 20%.
4 | Collaboration, Commitment | Increased government and non-government funding in alignment with HANWASH Core Values. | 3100a | Cumulative amount of money committed in alignment with HANWASH Core Values | $1 million in additional funds committed toward Mattson program | $2.5 million | $4.5 million | $7 million | $7.2 million in additional funds committed
Notes:
HANWASH is intended to be learning constantly from its work and iterating imporvements to its model. This will influence the way in which this framework is organized, objectives are established, and targets are set.
*Percentage point increase over baseline value.
Progress toward Year 5 indicator targets are shown as cumulative totals (e.g. 20% of approved interventions implemented in Year 3 includes the 10% implemented in Year 2).
"Approved interventions" means the specific interventions from the Commune Action Plans which are assigned to HANWASH by the Mayor's Offices.

## Monitoring framework
Organization: HANWASH
Document: Monitoring framework
Objective: Track program indicators over time.
Scope: Mattson Program
Reference link: This document
Version number: 2.41
Version date: Oct 03, 2023
Notes: Please duplicate this sheet for each implementing partner and use formulae to calculate the combined values here.
Objectives |  |  |  | Targets
| Indicator |  |  | End of Project | FY 2024 |  | FY 2025 |  | FY 2026 |  | FY 2027 |  | FY 2028
Program | Code | Description | Units |  | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual
Mattson | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Mattson | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Mattson | 1100a | % of commune WASH events with Rotarian participation | % of commune level events reported | 80% | TBD |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 1110a | # of volunteer hours per month spent by Rotarians in WASH events | volunteer hours / club / month | 25.5 | TBD |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 1120a | # of ambassadors who have completed training | people | 22 | First cohort |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 1120b | # of coordinators who have completed training | people | 9 | First cohort |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 1200a | % of approved interventions implemented in alignment with Commune Action Plans | % of implemented activities | 90% | Commune Action Plans are finalized as necessary |  | TBD |  | TBD |  | TBD |  | 90%
Mattson | 1210a | # of communes with action plans that explicitly include each W,S,H,WRM aspect (water, sanitation, hygiene, water resources management) | communes | 5 | mWater platform fully operational |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 1220a | # of WASH planning and coordination events with DINEPA and municipal officials | events/month | 5 | TBD |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 1300a | % of service providers under HANWASH initiative monitored according to national guidelines | % of service providers in intervention communes | 100% | mWater platform fully operational |  | TBD |  | TBD |  | TBD |  | 100%
Mattson | 1300b | % of intervention service providers with accountability structures in place | % of intervention water points | 75% | TBD |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 1310a | # of intervention water systems regularly reporting data | water systems | 5 | TBD |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 1310c | Average response time to resolve customer complaints | Days | 80% | TBD |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 1320a | # of communes which have held an annual service provider review with key stakeholders in the last year | communes | 5 | TBD |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Mattson | 2100a | % of intervention water points which are functioning and potable | % of intervention water points | 75% | 90% |  | 85% |  | 80% |  | 80% |  | 75%
Mattson | 2100b | % of population in intervention communes with at least basic drinking water service | % of people in the commune | 90% | Baseline study carried out and documented |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 2100c | % of population in intervention communes with safely managed drinking water service | % of people in the commune | 40% | TBD |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 2110a | # of people in intervention communes with access to basic drinking water service through community managed water points | people | 100000 | 10000 |  | 30000 | 25000 | 60000 | 55000 | 80000 | 83000 | 100000
Mattson | 2110b | # of community managed water points created | water points | 400 | 40 |  | TBD |  | TBD |  | TBD |  | 400
Mattson | 2120a | # of people added to safely managed drinking water service | people | 27500 | TBD |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 2120b | # of professionally managed piped water systems created in the intervention communes | water systems | 5 | TBD |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 2200a | % of intervention communities which are verified ODF | % of intervention communities | 75% | TBD |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 2200b | % of population in intervention communes with at least basic sanitation service | % of people in the commune | 85% | Baseline study carried out and documented |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 2200c | % of population in intervention communes with safely managed sanitation service | % of people in the commune | TBD | TBD |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 2210a | # of people added to basic sanitation service in the intervention communes | people | 75000 | 10000 |  | TBD |  | TBD |  | TBD |  | 100000
Mattson | 2210b | # of "intervention" communities verified ODF | communities | 300 | 40 |  | TBD |  | TBD |  | TBD |  | 400
Mattson | 2220a | # of "intervention" communities certified ODF | communities | 225 | TBD |  | TBD |  | TBD |  | TBD |  | TBD
HANWASH - Master | 2230a | # of public latrines constructed | toilet blocks | 300 | 30 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 300 | TBD
Mattson | 2300a | % of population in intervention communes with at least basic hygiene service | % of people within intervention communities | 75000 | Baseline study carried out and documented |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 2300b | % of population in intervention communes with basic hygiene service | % of people in the commune | 100000 | 10000 |  | TBD |  | TBD |  | TBD |  | 100000
Mattson | 2310a | # of community animators trained | animators | 10 | First cohort |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 2320a | # of people added to basic hygiene service | people | 5 | First cohort |  | TBD |  | TBD |  | TBD |  | TBD
HANWASH - Master | 2400a | % of schools with basic drinking water, sanitation, and hygiene services | % of intervention schools |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
HANWASH - Master | 2400b | % of healthcare facilities with basic drinking water, sanitation, and hygiene services | % of intervention schools |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
HANWASH - Master | 2410a | # of schools added with basic drinking water services | schools |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
HANWASH - Master | 2410b | # of healthcare facilities added with basic drinking water services | healthcare facilities |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
HANWASH - Master | 2420a | # of schools added with basic sanitation services | schools |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
HANWASH - Master | 2420b | # of healthcare facilities added with basic sanitation services | healthcare facilities |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
HANWASH - Master | 2430a | # of schools added with basic hygiene | schools |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
HANWASH - Master | 2430b | # of healthcare facilities added with basic hygiene | healthcare facilities |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Mattson | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Mattson | 3100a | Cumulative amount of money committed in alignment with HANWASH Core Values | USD | 9600000 | 3800000 |  | TBD |  | TBD |  | TBD |  | 9600000
Mattson | 3100b | % of committed money which has been spent (cumulative) | % of amount committeed | 100% | TBD |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 3110a | Amount of money spent by external actors within HANWASH project areas | USD | 7200000 | TBD |  | TBD |  | TBD |  | TBD |  | TBD
HANWASH - Master | 3120a | Amount of money spent by external actors beyond project areas in alignment with HANWASH Core Values | USD | 0 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Mattson | 3200a | % of implementing partners in HANWASH program areas who have signed the DINEPA Accord Cadre | % of implementing partners in HANWASH program areas | 100% | TBD |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 3210a | # of DINEPA personnel trained as leaders | people | 120 | First cohort |  | TBD |  | TBD |  | TBD |  | TBD
Mattson | 3220a | # of technical trainings provided for DINEPA priority areas | trainings | 5 | TBD |  | TBD |  | TBD |  | TBD |  | TBD
Note on E15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is difficult because there will be a vast number of meetings held by implementing partners in communities. Should we limit the denominator here to "commune level events"?
Note on E16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5-7 hrs per week per club Reply: Paid staff don't count towards volunteer hours.
Note on E17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (from Mattson Proposal)
Note on F17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How many are in the first cohort?
Note on E18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Carribean countries?
Note on F18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How many are in the first cohort?
Note on E19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It isn't feasible that the Commune Action Plan perfectly align with the Mattson Proposal plan, but a majority of activities should be aligned.
Note on E21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: One event per intervention commune per month
Note on E28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Estimation based on functionality rate for Haiti Outreach (2005-2020)
Note on E31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 400 communities x 250 people per community
Note on F31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From "Performance objectives" document (10000 people)
Note on N31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From performance objectives (50,000 people)
Note on E32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 400 communities (from Mattson Proposal)
Note on F32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10,000 people / 250 people per community
Note on N32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 50,000 people / 250 people per community
Note on E33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Maybe 1,000 HH/water system (highly dependent on feasibility studies)
Note on E34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5 systems (from Mattson Proposal)
Note on E35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 75% of completed communities. Need to estimate this from HO and UNICEF projects.
Note on E37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to discuss % treated in-situ and % offsite treatment. The latter can be either SOIL or STEB (Station de traitement d'eaus usées et boues).
Note on E38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 400 communities x 250 people per community
Note on F38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From "Performance objectives" document (10000 people)
Note on E39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 75% of completed communities x 400 completed communities
Note on F39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2000 households / 5.5. people per household * 250 people per community
Note on E40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 75% x # verified ODF will maintain this status for at least 1 year.
Note on E41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 400 communities x 75% monitored for ODF
Note on F41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 75% of communities verified ODF
Note on E42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 75% of people in completed communities x 400 completed communities x 250 people per community
Note on E43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 400 communities x 250 people per community
Note on F43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From "Performance objectives" document (10000 people)
Note on E44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 / commune x 5 communes
Note on F44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How many are in the first cohort?
Note on E45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5 of the 7 communes (from Mattson Proposal)
Note on F45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How many are in the first cohort?
Note on E60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be discussed
Note on F60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How many are in the first cohort?

## Core values
Organization: HANWASH
Document: HANWASH Core Values
Objective: Define the Core Values which guide HANWASH decision making
Scope: HANWASH
Reference link: TBD
Version number: 1.0
Version date: Sept 22, 2023
HANWASH Core Values
# | Value | Factor | Description
1 | Locally-led | Localization | We support community leadesrhip in governance of WASH infrastructure and services.
2 | Collaborative | Collaboration | Volunteers, government authorities, and partners are engaged in a meaningful way.
3 | Systematic | Systematization | We will be thoughtful and consistent in planning, doing, and improving our work.
4 | Impactful | Impact | Sustainability is a key metric of our success.
5 | Committed | Commitment | We will not stop until the job is done.