## Feuil1
|  | February |  |  |  | March |  |  |  | April
|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Deliverable 1 | One (1) page on mWater to view/query Haiti Outreach data associated with Adopt-a-Wells completed or currently in progress in the commune of Cavaillon; / One (1) page on mWater to view/query data associated with the operation of the Pignon town water utility
Activities | One-hour weekly Meetings
Review OF the Hanwash system | bar: February Week 1 to February Week 3
Review the database | bar: February Week 1 to February Week 3
Think-Thank the structure of a user console | bar: February Week 4
Identify the Haiti Outreach Adopt a Wells data source (cavaillon) | bar: February Week 4
Identify the Haiti Outreach Town Utilities data source (pignon) | bar: February Week 4
Build an iteration of this user console
Deployment of the two pages to get feedback from the team
Design training presentation on ppt about how to use the two created pages
Integration of the feedback from the team | bar: March Week 6
Training sessions for the volunteers on the use of the two created pages
Final Deployment of the two pages to the Volunteers/ other stakeholders
Deliverable 2 | One (1) page on mWater which allows us to query the Commune Action Plan data for Cavaillon, Ferrier, Leogane, Pignon, and Terre-Neuve
Activities | Identify the Commune Action Plan data (Cavaillon, Ferrier, Leogane, Pignon et Terre-Neuve)
Build an iteration of the "Commune Action Plan" user console
Deployment of the page to the feedback team
Design training presentation for the created page
Integration of feedback from the team
Training sessions for the ambassadors
Final deployment for the Ambassadors
Deliverable 3 | Contribution to the overall development of the mWater database as a user-friendly portal for HANWASH volunteers and staff to easily access project data, regardless of whether it is the construction or the operations period.