## Feuil1
|  | February |  |  |  | March |  |  |  | April
|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Deliverable
Activities | Meetings
Review OF the Hanwash system | bar: February Week 1 to February Week 3
Review the database | bar: February Week 1 to February Week 3
Think-Thank the struture of a user console | bar: February Week 4
ID the Haiti Outreach Adopt a Wells data source (cavaillon)(Pignon) | bar: February Week 4
ID the Haiti Outreach Town Utilities data source (pignon)(Cavaillon) | bar: February Week 4
Build an iteration of this user console
Deployment for the feedback team
Design training presentation for set console
Take feedback from the team | bar: March Week 6
Training sessions for the volunteers
Deployment for the Volunteers
ID the Commune Action Plan data (Cavaillon, Ferrier, Leogane, Pignon et Terre-Neuve)
Build an iteration of the "Commune Action Plan" user console
Deployment for the feedback team
Design training presentation for set console
Take feedback from the team
Training sessions for the ambassadors
Deployment for the Ambassadors
Tidying up activies on the Hanwash Home