## Sheet1
ID | Indicator_group | Category | Category_code | Category_code_description | Indicator | Definitions | Units | Baseline_value | End_of_program_target | Year1_target | Year1_actual | Year2_target | Year2_actual | Year3_target | Year3_actual | Year4_target | Year4_actual | Year5_target | Year5_actual
1 | Mattson LM | Ultimate outcome | 1 | Increased access to safe, sustainable and affordable water, sanitation and hygiene (WASH) services in Haiti​. | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Mattson LM | Intermediate outcome | 1000 | Strengthened demand for and management of WASH services in communes. | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1100a | Mattson LM | Immediate outcome | 1100 | Increased civil society engagement in decision making and implementation of WASH services. | % of commune WASH events with Rotarian participation | This indicator measures the level of engagement and support provided by Rotarians in WASH-related events in local communes, reflecting increased civil society engagement in WASH services. | % | 20 | 100 | 20 | 20 | 21 | 21 | 28 | 22 | 49 | 45 | 62 | 72
1100b | Mattson LM | Immediate outcome | 1100 | Increased civil society engagement in decision making and implementation of WASH services. | % of commune WASH events led by trained HANWASH Ambassadors and Coordinators to communicate WASH messages and advocate for HANWASH goal | The percentage of WASH events within communes that are led and coordinated by trained HANWASH Ambassadors and Coordinators, aiming to effectively communicate WASH messages and advocate for HANWASH goals. This reflects the level of leadership and initiative taken by trained personnel in promoting WASH activities. | % | 20 | 100 | 20 | 20 | 27 | 25 | 35 | 35 | 42 | 37 | 56 | 63
1110a | Mattson LM | Outputs | 1110 | Support civil society engagement in the WASH sector.​ | # of volunteer hours per month spent by Rotarians in WASH events | The total number of hours that Rotarians volunteer each month participating in WASH initiatives and activities. | volunteer hours / club / month | 1 | 100 | 2 | 1 | 4 | 3 | 12 | 2 | 33 | 22 | 53 | 76
1110b | Mattson LM | Outputs | 1110 | Support civil society engagement in the WASH sector.​ | Number of people reached by the HANWASH Ambassadors, Coordinators and Rotarians in general in the Commune WASH events and advocacy efforts led by them | The total number of individuals who participate in or are impacted by WASH events and advocacy efforts led by HANWASH Ambassadors, Coordinators, and Rotarians. This indicates the outreach and engagement success of the WASH programs. | people | 1 | 100 | 2 | 1 | 9 | 2 | 17 | 1 | 21 | 13 | 55 | 87
1120a | Mattson LM | Outputs | 1120 | Train HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean.​ | # of ambassadors who have completed training | The total number of HANWASH Ambassadors who have successfully completed their training programs. | people | 1 | 100 | 1 | 1 | 3 | 1 | 4 | 2 | 16 | 8 | 80 | 92
1120b | Mattson LM | Outputs | 1120 | Train HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean.​ | # of coordinators who have completed training | The total number of HANWASH Coordinators who have successfully completed their training programs. | people | 1 | 100 | 1 | 1 | 11 | 1 | 18 | 4 | 23 | 19 | 51 | 79
1120c | Mattson LM | Outputs | 1120 | Train HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean.​ | # of training materials created in alignment with HANWASH three pillars and core values | The total count of educational and training materials developed that adhere to the three pillars and core values of HANWASH. | Training materials | 1 | 20 | 1 | 1 | 1 | 1 | 2 | 2 | 4 | 3 | 16 | 17
1120d | Mattson LM | Outputs | 1120 | Train HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean.​ | # of hours of training received by the HANWASH Ambassadors & Coordinators and their committees throughout the Caribbean | Number of hours and number of people attending | Hours of training | 1 | 40 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 37 | 39
1200a | Mattson LM | Immediate outcome | 1200 | Improved commune WASH planning and coordination by local authorities.​ | % of approved interventions implemented in alignment with Commune Action Plans | The percentage of WASH interventions that have been approved and implemented in accordance with predefined Commune Action Plans, ensuring the initiatives are part of a strategic and coordinated approach to WASH improvements. | % | 20 | 100 | 20 | 20 | 20 | 20 | 22 | 22 | 23 | 20 | 95 | 98
1210a | Mattson LM | Outputs | 1210 | Create or improve commune action plans that focus on water, sanitation and hygiene, and water resource management.​ | # of communes with action plans that explicitly include each W,S,H,WRM aspect (water, sanitation, hygiene, water resources management) | The number of communes that have developed action plans explicitly addressing water, sanitation, hygiene, and water resources management. | communes | 1 | 12 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 10 | 10
1220a | Mattson LM | Outputs | 1220 | Facilitate coordination meetings between commune WASH stakeholders. | # of WASH planning and coordination events with DINEPA and municipal officials | The number of meetings and events held to plan and coordinate WASH activities involving DINEPA and municipal officials. | events/month | 1 | 10 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 8 | 10
1300a | Mattson LM | Immediate outcome | 1300 | Improved accountability of service providers to users of WASH services.​ | % of service providers under HANWASH initiative monitored according to national guidelines | The percentage of service providers participating in the HANWASH initiative that are regularly monitored according to established national guidelines. This metric ensures that WASH service providers meet accountability standards, maintain quality service delivery, and uphold their responsibilities towards users as per national regulatory requirements. | % | 20 | 100 | 21 | 21 | 21 | 20 | 24 | 21 | 39 | 31 | 75 | 87
1300b | Mattson LM | Immediate outcome | 1300 | Improved accountability of service providers to users of WASH services.​ | % of intervention service providers with accountability structures in place | The percentage of service providers with established accountability mechanisms, such as regular meetings, community engagement, bylaws, fee collection, record-keeping, and monthly reporting to local authorities. | % | 20 | 100 | 23 | 21 | 30 | 22 | 33 | 32 | 40 | 31 | 54 | 74
1300c | Mattson LM | Immediate outcome | 1300 | Improved accountability of service providers to users of WASH services.​ | % of users being satisfied with the quality, affordability and reliability of the WASH services provided | This indicator measures the proportion of the households connected to the water system which are satisfied with the quality, affordability and reliability of the WASH services provided | % | 20 | 100 | 21 | 21 | 29 | 25 | 38 | 22 | 44 | 32 | 48 | 80
1310a | Mattson LM | Outputs | 1310 | Monitor WASH service performance and satisfaction. | # of intervention water systems regularly reporting data | The number of water systems within intervention areas that consistently submit monthly operational and performance reports, ensuring regular monitoring and transparency of water service delivery. | water systems | 1 | 10 | 1 | 1 | 1 | 1 | 4 | 2 | 4 | 1 | 4 | 9
1310b | Mattson LM | Outputs | 1310 | Monitor WASH service performance and satisfaction. | % of customer complaints resolved during the month | The percentage of customer complaints that are resolved within the same month they are identified. | % | 20 | 100 | 22 | 20 | 29 | 26 | 30 | 23 | 33 | 21 | 66 | 90
1310c | Mattson LM | Outputs | 1310 | Monitor WASH service performance and satisfaction. | Average response time to resolve customer complaints | This indicator measures how long it takes on average for the service providers to resolve customer complaints. | Days | 7 | 21 | 7 | 7 | 7 | 7 | 7 | 7 | 11 | 10 | 17 | 18
2000 | Mattson LM | Intermediate outcome | 2000 | Enhanced household access to and use of sustainable, affordable, and safe water, sanitation and hygiene services.​ | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2100a | Mattson LM | Immediate outcome | 2100 | Increased household access to sustainable, affordable, and safe drinking water services.​ | % of intervention water points which are functioning and potable | The percentage of water points in intervention areas that are operational (either fully functional or functional with minor repairs needed) and provide potable water, free from E. Coli and other priority contaminants, according to original design specifications. | % | 20 | 100 | 26 | 24 | 27 | 21 | 27 | 26 | 31 | 24 | 69 | 85
2100b | Mattson LM | Immediate outcome | 2100 | Increased household access to sustainable, affordable, and safe drinking water services.​ | % of population in intervention communes with at least basic drinking water service | The percentage of people in intervention communes who have access to an improved water source within a 30-minute round trip, ensuring basic drinking water service at the household level. | % | 20 | 100 | 22 | 22 | 31 | 31 | 35 | 21 | 44 | 43 | 48 | 63
2100c | Mattson LM | Immediate outcome | 2100 | Increased household access to sustainable, affordable, and safe drinking water services.​ | % of population in intervention communes with safely managed drinking water service | The percentage of people in target areas who have access to safe drinking water that is always available, accessible at home, and free from contaminants. | % | 20 | 100 | 20 | 20 | 20 | 20 | 20 | 20 | 34 | 22 | 86 | 98
2100d | Mattson LM | Immediate outcome | 2100 | Increased household access to sustainable, affordable, and safe drinking water services.​ | % of intervention water points which are functional, potable, and have a balanced budget or a budget with surplus after 2 years | The percentage of water points in intervention areas that are fully operational, provide potable water, and maintain a balanced or surplus budget within two years from their inauguration date. | % | 20 | 100 | 20 | 20 | 22 | 22 | 22 | 21 | 40 | 25 | 76 | 92
2110a | Mattson LM | Outputs | 2110 | Develop community managed water points. | # of people in intervention communes with access to basic drinking water service through community managed water points | The number of individuals in intervention communes who benefit from access to basic drinking water services provided by community-managed water points, ensuring sustainable and locally-managed water supply solutions. | people | 1 | 100 | 1 | 1 | 2 | 1 | 2 | 1 | 31 | 22 | 68 | 79
2110b | Mattson LM | Outputs | 2110 | Develop community managed water points. | # of community managed water points created | The total number of water points established and managed by local communities under DINEPA's guidelines. | water points | 1 | 200 | 2 | 2 | 3 | 2 | 14 | 9 | 82 | 44 | 103 | 147
2110c | Mattson LM | Outputs | 2110 | Develop community managed water points. | % of the community managed water points created which submit report to local authorities on a monthly basis | The percentage of community-managed water points that submit monthly reports to local authorities. | water points | 1 | 200 | 15 | 7 | 22 | 18 | 22 | 15 | 28 | 24 | 117 | 140
2120a | Mattson LM | Outputs | 2120 | Rehabilitate and expand professionally operated piped water systems. | # of people added to safely managed drinking water service | The number of individuals who have gained access to safe drinking water through the project. | people | 1 | 100 | 1 | 1 | 2 | 2 | 11 | 11 | 18 | 14 | 72 | 76
2120c | Mattson LM | Outputs | 2120 | Rehabilitate and expand professionally operated piped water systems. | # of professionally managed piped water systems rehabilitated in the intervention communes | The number of existing piped water systems that have been restored to proper functionality in the target areas. | water systems | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 10 | 10
2120b | Mattson LM | Outputs | 2120 | Rehabilitate and expand professionally operated piped water systems. | # of professionally managed piped water systems created in the intervention communes | The number of new piped water systems established and professionally managed in the target areas. | water systems | 1 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 8 | 8
2200a | Mattson LM | Immediate outcome | 2200 | Increased household access to sustainable, affordable, and safe sanitation services.​ | % of intervention communities which are verified ODF | The percentage of communities in intervention areas that have been verified as Open Defecation Free by the commune WASH committee, meeting criteria such as the presence of usable toilets, no fecal matter in open areas, and willingness to maintain ODF status. | % | 20 | 100 | 20 | 20 | 20 | 20 | 27 | 27 | 32 | 32 | 81 | 81
2200b | Mattson LM | Immediate outcome | 2200 | Increased household access to sustainable, affordable, and safe sanitation services.​ | % of population in intervention communes with at least basic sanitation service | The percentage of people in intervention communes who have access to improved and unshared sanitation facilities, ensuring basic sanitation service at the household level. | % | 20 | 100 | 20 | 20 | 23 | 23 | 27 | 21 | 43 | 34 | 67 | 82
2200c | Mattson LM | Immediate outcome | 2200 | Increased household access to sustainable, affordable, and safe sanitation services.​ | % of population in intervention communes with safely managed sanitation service | The percentage of people in target areas who have access to safe, private (unshared) sanitation facilities where excreta are properly treated on-site or transported and treated off-site. | % | 20 | 100 | 20 | 20 | 20 | 20 | 21 | 21 | 25 | 23 | 94 | 96
2210a | Mattson LM | Outputs | 2210 | Mobilize communities to achieve Open Defecation Free status | # of people added to basic sanitation service in the intervention communes | The number of individuals newly provided with access to basic sanitation services, including improved and unshared facilities, within intervention communes. | people | 1 | 100 | 1 | 1 | 2 | 2 | 2 | 1 | 28 | 7 | 71 | 93
2210b | Mattson LM | Outputs | 2210 | Mobilize communities to achieve Open Defecation Free status | # of "intervention" communities verified ODF | The total number of communities in intervention areas that have achieved verification as Open Defecation Free, meeting the criteria set by the commune WASH committee. | communities | 1 | 200 | 1 | 1 | 8 | 3 | 49 | 18 | 66 | 5 | 80 | 177
2220a | Mattson LM | Outputs | 2220 | Certify the sustained usage of sanitation services. | # of "intervention" communities certified ODF | The number of communities in intervention areas that have sustained Open Defecation Free status for at least one year and have been officially certified by the commune WASH committee. | communities | 1 | 200 | 5 | 2 | 13 | 6 | 13 | 7 | 24 | 9 | 149 | 180
2230a | Mattson LM | Outputs | 2230 | Construct public latrines. | # of public latrines constructed | The number of public latrines built within the project scope. | toilet blocks | 1 | 150 | 3 | 3 | 12 | 11 | 38 | 29 | 43 | 10 | 58 | 101
2300a | Mattson LM | Immediate outcome | 2300 | Increased household access to hygiene services. | % of population in intervention communes with at least basic hygiene service | The percentage of people in intervention communes who have access to facilities with soap and water for handwashing, ensuring basic hygiene service at the household level. | % | 20 | 100 | 21 | 20 | 22 | 21 | 26 | 26 | 42 | 31 | 69 | 82
2300b | Mattson LM | Immediate outcome | 2300 | Increased household access to hygiene services. | % of population in intervention communes with basic hygiene service | The percentage of individuals newly provided with access to basic hygiene services, including handwashing facilities with soap and water within intervention communes. | % | 20 | 100 | 24 | 24 | 25 | 24 | 26 | 24 | 28 | 23 | 77 | 85
2310a | Mattson LM | Outputs | 2310 | Train skilled community animators to deliver hygiene trainings and community mobilization.​ | # of community animators trained | The total number of community animators who have completed training programs. | animators | 1 | 100 | 2 | 1 | 5 | 3 | 10 | 9 | 17 | 15 | 70 | 76
2310b | Mattson LM | Outputs | 2310 | Train skilled community animators to deliver hygiene trainings and community mobilization.​ | # of hours of hygiene trainings and community mobilization provided by the community animators trained | This indicator measures the intensity of the hygiene trainings and community mobilization delivered by the community animators. It is the sum of hours the community animator spends providing hygiene trainings. | Hours | 1 | 100 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 98 | 99
2320a | Mattson LM | Outputs | 2320 | Certify the sustained usage of hygiene services. | # of people added to basic hygiene service | The number of individuals newly provided with access to basic hygiene services, including handwashing facilities with soap and water within intervention communes. | people | 1 | 100 | 1 | 1 | 3 | 3 | 3 | 1 | 21 | 18 | 76 | 81
2400a | HANWASH-Master LM | Immediate outcome | 2400 | Increased access to sustainable, safe drinking water, sanitation, and hygiene materials in healthcare facilities, schools, and public places. | % of schools with basic drinking water, sanitation, and hygiene services | The percentage of schools in intervention areas that have improved, safe drinking water sources, functional sanitation facilities, and handwashing stations with soap and water. | % | 20 | 100 | 20 | 20 | 20 | 20 | 22 | 22 | 22 | 20 | 96 | 98
2400b | HANWASH-Master LM | Immediate outcome | 2400 | Increased access to sustainable, safe drinking water, sanitation, and hygiene materials in healthcare facilities, schools, and public places. | % of healthcare facilities with basic drinking water, sanitation, and hygiene services | The percentage of healthcare facilities in intervention areas that have improved, safe drinking water sources, functioning sanitation facilities, and handwashing stations with soap and water or alcohol-based hand rubs. This metric ensures that healthcare facilities meet basic WASH standards. | % | 20 | 100 | 20 | 20 | 20 | 20 | 20 | 20 | 36 | 30 | 84 | 90
2410a | HANWASH-Master LM | Outputs | 2410 | Construct or rehabilitate water supply for healthcare facilities and schools. | # of schools added with basic drinking water services | The total number of schools in intervention areas that have been provided with access to improved drinking water services, ensuring that they meet the required standards of water quality and availability. | schools | 1 | 200 | 3 | 2 | 6 | 5 | 39 | 24 | 59 | 6 | 97 | 167
2410b | HANWASH-Master LM | Outputs | 2410 | Construct or rehabilitate water supply for healthcare facilities and schools. | # of healthcare facilities added with basic drinking water services | The total number of healthcare facilities in intervention areas that have been provided with access to improved drinking water services, ensuring safe and reliable water for patients and staff. | healthcare facilities | 1 | 200 | 2 | 1 | 4 | 2 | 7 | 7 | 44 | 38 | 147 | 156
2420a | HANWASH-Master LM | Outputs | 2420 | Construct communal, healthcare facility, and school latrines. | # of schools added with basic sanitation services | The total number of schools in intervention areas that have been equipped with improved, functional sanitation facilities, including gender-separated and accessible toilets, to meet the needs of students and staff. | schools | 1 | 200 | 3 | 2 | 3 | 2 | 16 | 13 | 19 | 14 | 163 | 173
2420b | HANWASH-Master LM | Outputs | 2420 | Construct communal, healthcare facility, and school latrines. | # of healthcare facilities added with basic sanitation services | The total number of healthcare facilities in intervention areas that have been equipped with improved, functional sanitation facilities, including dedicated and accessible toilets. These facilities are designed to meet the sanitation needs of all healthcare users. | healthcare facilities | 1 | 200 | 2 | 1 | 2 | 1 | 36 | 17 | 67 | 58 | 97 | 127
2430a | HANWASH-Master LM | Outputs | 2430 | Work with (local authorities, civil society) to ensure access to soap or alcohol-based handrub at schools and healthcare facilities. | # of schools added with basic hygiene | The total number of schools in intervention areas that have been provided with handwashing facilities, including soap and water, ensuring basic hygiene practices are accessible to all students and staff. | schools | 1 | 200 | 1 | 1 | 1 | 1 | 5 | 4 | 53 | 21 | 144 | 177
2430b | HANWASH-Master LM | Outputs | 2430 | Work with (local authorities, civil society) to ensure access to soap or alcohol-based handrub at schools and healthcare facilities. | # of healthcare facilities added with basic hygiene | The total number of healthcare facilities in intervention areas that have been provided with handwashing facilities, including soap and water or alcohol-based hand rubs, ensuring basic hygiene practices are accessible to all patients and staff. | healthcare facilities | 1 | 200 | 5 | 5 | 12 | 9 | 12 | 12 | 43 | 37 | 132 | 141
3000 | Mattson LM | Intermediate outcome | 3000 | Expanded reach and resources leveraged through collective action with other national and international actors.​ | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3100a | Mattson LM | Immediate outcome | 3100 | Increased government and non-government funding in alignment with HANWASH Core Values. | Cumulative amount of money committed in alignment with HANWASH Core Values | The total amount of funds pledged by stakeholders in accordance with HANWASH Core Values. | USD | 500 | 20000 | 500 | 500 | 501 | 500 | 501 | 501 | 856 | 745 | 19642 | 19754
3100b | Mattson LM | Immediate outcome | 3100 | Increased government and non-government funding in alignment with HANWASH Core Values. | % of committed money which has been spent (cumulative) | The cumulative percentage of allocated funds that have been spent over the project duration. This metric is calculated by dividing the total amount spent by the total committed funds and multiplying by 100, reflecting the financial resource utilization efficiency of the project. | % | 20 | 100 | 21 | 20 | 24 | 22 | 26 | 21 | 38 | 32 | 71 | 85
3110a | Mattson LM | Outputs | 3110 | Mobilize and coordinate funding from government and non-government sources in HANWASH program areas in alignment with HANWASH Core Values. | Amount of money spent by external actors within HANWASH project areas | The total amount of money spent by external organizations or entities within the areas covered by HANWASH projects. | USD | 500 | 20000 | 1359 | 1309 | 2208 | 913 | 2857 | 1330 | 3468 | 1713 | 12108 | 16735
3120a | Mattson LM | Outputs | 3120 | Mobilize and influence funding from government and non-government sources beyond HANWASH program areas in alignment with HANWASH Core Values. | Amount of money spent by external actors beyond project areas in alignment with HANWASH Core Values | The total amount of money spent by external entities outside the HANWASH project areas, in line with HANWASH Core Values. | USD | 500 | 20000 | 767 | 641 | 1139 | 1062 | 2191 | 1775 | 6765 | 681 | 11138 | 17841
3200a | Mattson LM | Immediate outcome | 3200 | Increased capacity of DINEPA to regulate the sector and OREPA to oversee and support implementation. | % of implementing partners in HANWASH program areas who have signed the DINEPA Accord Cadre | Number of IPs who have signed Total number of IPs in HANWASH program areas x 100 | % | 20 | 100 | 22 | 21 | 23 | 20 | 25 | 23 | 33 | 32 | 77 | 84
3210a | Mattson LM | Outputs | 3210 | Conduct leadership training of DINEPA and OREPA personnel. | # of DINEPA personnel trained as leaders | The total number of DINEPA personnel who have undergone leadership training programs. | people | 1 | 100 | 1 | 1 | 1 | 1 | 7 | 3 | 36 | 14 | 59 | 85
3220a | Mattson LM | Outputs | 3220 | Provide technical assistance and training to DINEPA and the OREPAs. | # of technical trainings provided for DINEPA priority areas | The number of technical training sessions delivered to address DINEPA's prioritized areas, including the unified national tariff methodology and ODF certification for 2023-24. | trainings | 1 | 100 | 1 | 1 | 1 | 1 | 10 | 3 | 27 | 10 | 65 | 89