## Sheet1
Deliverables | task | status | comments
1 | HANWASH PERFORMANCE INDICATOR console is built | 100%
1 | SAEP console is built | 100%
1 | Training session (Haiti Liaison [Marlene, Wildaine, Nixon]; Steering Committee [Barb Spangler]; M&E committee [Tristam]; Ambassador[Fritz, Wildaine]; D7020) | 100%
2 | The core HANWASH stakeholders (subcommittee leaders, the ambassadors leaders, project team leaders, HANWASH Staff, consultants) and the mayors have a functional mWater account with the desired format: first_name.last_name | 73% | 12 accounts from 43 need to be created to complete this task
2 | The new organization of the HANWASH protal structure is built | 100%
2 | 50% of the core stakeholders have at least visited the HANWASH PORTAL ounce a week within the last month | 100% | we got 55% over the 30 days (20 October 2024 - 20 November 2024).
3 | Data quality check for the consoles and the new structure of the HANWASH portal is validated | 25%
3 | Water Point Committee / Commite Point d'Eau (CPE) console is build for the OREPA and local authorities | 100%
3 | User guides for the CPE console in English and Creole. Training session is conducted for the Haiti Liason leaders, mayors, tepac, ambassadors etc. | 20% | user guides is completed, not validated yet
3 | Training and support / Ongoing towards the mayors, the commitees, contractors, ambassadors. | 50%